## Flight Test Matrix - Overview
| Completed: |  | 84.77% |  | 197 | 167
| Mass and Balance | [5 empty] | Flaps |  |  |  | Symmetry |  | Speed |  |  |  | Power |  |  | Altitude |  |  |  | Amount |  | Duration [min]
| Light | Medium | Heavy | Fwd | Centre | Aft | Up | 10° | 25° | 40° | - | oposite | Min | Low | Med | High | Low | Med | Max | - | Low | Medium | High | Repeats | Number | Manoeuvre | Total
Short Period Manoeuvre #1 |  | 1 |  | 1 |  | 1 | 1 |  |  |  | 1 | 1 | 1 |  | 1 | 1 |  | 1 |  |  |  | 1 | 1 | 2 | 48 | 3 | 144
Short Period Manoeuvre #2 |  | 1 |  | 1 |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  | 1 |  | 1 |  |  | 1 |  | 2 | 4 | 3 | 12
Phugoid Manoeuvre |  | 1 |  | 1 |  | 1 | 1 |  |  |  | 1 | 1 |  |  | 1 |  |  | 1 |  |  |  | 1 | 1 | 2 | 16 | 5 | 80
Pushover-pull-up |  | 1 |  | 1 |  | 1 | 1 |  |  |  | 1 |  |  |  | 1 |  |  | 1 |  |  |  | 1 |  | 2 | 4 | 5 | 20 | remove
Level turn |  | 1 |  | 1 |  |  | 1 |  |  |  | 1 | 1 |  |  | 1 |  |  | 1 |  |  |  | 1 |  | 2 | 4 | 3 | 12
Thrust variation |  | 1 |  | 1 |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  | 1 |  |  | 1 |  | 1 | 2 | 4 | 4 | 16
Bank-to-bank roll |  | 1 |  | 1 |  |  | 1 |  |  |  | 1 | 1 |  |  | 1 |  |  | 1 |  |  |  | 1 |  | 2 | 4 | 3 | 12
Dutch roll manoeuvre |  | 1 |  | 1 |  | 1 | 1 |  |  |  | 1 |  | 1 |  | 1 | 1 |  | 1 |  |  |  | 1 | 1 | 2 | 24 | 3 | 72
Steady heading steady sideslip #1 |  | 1 |  | 1 |  |  | 1 |  |  |  | 1 | 1 |  | 1 | 1 |  |  | 1 |  |  |  | 1 |  | 2 | 8 | 5 | 40
Steady heading steady sideslip #2 |  | 1 |  | 1 |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  | 1 |  | 1 |  |  | 1 |  | 2 | 4 | 5 | 20
T/O and Landing |  | 1 |  | 1 |  | 1 | 1 |  | 1 | 1 | 1 |  |  |  | 1 |  |  | 1 |  | 1 |  |  |  | 2 | 12 | 7 | 84
Go around |  | 1 |  | 1 |  |  |  |  | 1 |  | 1 |  |  |  | 1 |  |  | 1 |  | 1 |  |  |  | 2 | 2 | 7 | 14
Spiral-Check |  | 1 |  | 1 |  | 1 | 1 |  |  |  | 1 | 1 |  |  | 1 |  |  | 1 |  |  |  | 1 | 1 | 2 | 16 | 4 | 64
Stall |  | 1 |  | 1 |  | 1 | 1 | 1 |  |  | 1 |  |  |  | 1 |  |  | 1 |  |  |  | 1 |  | 2 | 8 | 5 | 40
[26 empty] | Test time [min] | 630
[26 empty] | Test time [h] | 10.5
[26 empty] | Time Margin | 1.9
[26 empty] | Total Time [h] | 19.95
| Mass |  |  |  | Balance | [6 empty] | Speed |  |  |  | Power (RPM, tbd) |  |  |  |  | Altitude
| Empty: |  | 706 kg |  | Max Fwd: |  | 83.8 in |  |  |  |  | Low |  | 70 |  | Low |  | descent |  |  | Low |  | 3500 ft
| Utility: |  | 916 kg |  | Max Aft: |  | 93 in |  |  |  |  | Medium |  | 80 |  | Medium |  | fly level |  |  | Medium |  | 5500 ft
| Normal: |  | 1106 kg | [8 empty] | High |  | 95 |  | High |  | climb |  |  | High |  | 6500 ft
[5 empty] | Fwd |  | 86 in
| Light: |  | 850 kg |  | Centre | [6 empty] | kn = KIAS
| Medium: |  | 930 kg |  | Aft |  | 89 in
| Heavy: |  | 1010 kg
| Limits | [10 empty] | High |  | 95 |  | High |  | climb |  |  | High |  | 6500 ft
| V_S | 2222 | 48 | [8 empty] | Low |  | 70 |  | Low |  | descent |  |  | Low |  | 3500 ft
| V_S | 1870 | 45 | [8 empty] | Medium |  | 80 |  | Medium |  | fly level |  |  | Medium |  | 5500 ft
Note on D2: ====== ID#AAAADLXwNNk Autor (2019-07-04 12:04:12) Anzahl Flüge - Pushover-pullup, Thrust variation, zero/full flap T/O
Note on N6: ====== ID#AAAADLXwNNc Autor (2019-07-04 12:04:12) nicht eher low?
Note on AA9: ====== ID#AAAADLXwNNs Autor (2019-07-04 12:04:12) inlcuding regaining of ALT
Note on A10: ====== ID#AAAADLXwNNw Autor (2019-07-04 12:04:12) nur ein Bank Angle? Coordinated turn?
Note on A11: ====== ID#AAAADLXwNNo Autor (2019-07-04 12:04:12) Do climb performance instead, when departing/returning? It is for performance validation? AND: only on one altitude?
Note on V11: ====== ID#AAAADLXwNNY Autor (2019-07-04 12:04:12) mixer? Note positions! (FlightTestCard)
Note on A12: ====== ID#AAAADLXwNOU Autor (2019-07-04 12:04:12) Do this before dutch roll
Note on A13: ====== ID#AAAADLXwNN8 Autor (2019-07-04 12:04:12) do this after bank-to-bank
Note on A16: ====== ID#AAAADNk1yxg Autor (2019-07-04 12:04:12) T/O Zero and Full Flaps not done
Note on J17: ====== ID#AAAADLXwNOY Autor (2019-07-04 12:04:12) transition
Note on A18: ====== ID#AAAADLXwNOA Autor (2019-07-04 12:04:12) offsett bankangle Does A/C come back or diverge?
Note on H19: ====== ID#AAAADLXwNOQ Autor (2019-07-04 12:04:12) Stall without flaps?
Note on AA22: ====== ID#AAAADLXwNN4 Autor (2019-07-04 12:04:12) Time required for airport leave/return and 10% margin for errorous tests

## Finanzen
Verfügbar |  | 12000 |  |  | Flugminute Hans: | 6.4167 |  | Hans | 687 | 1145 | 11.45
Bau |  | -1000.55 |  |  | Flugminute Dave: | 7.25 |  | Dave | 65 | 162.5 | 1.0833
Mechaniker |  | -2990 |  |  | Landung LSPV: | 13
Standzeit |  | -1766.3333 |  |  | Start LSZN: | 25
Flüge |  | -5428.5
Total |  | 814.6167
Datum | Flug | Flugzeit [min] | Landungen | Kosten | Programm | Pilot | Flight Test Engineer
2019-05-14 | C_H | 70 | 1 | 474.1667 | Checkflug Hans | Hans | -
2019-05-07 | C_D | 30 | 1 | 242.5 | Checkflug Dave | Dave | -
2019-06-03 | M1 | 30 | 1 | 217.5 | Hinflug Einbau | Hans | -
2019-06-05 | M2 | 15 | 1 | 121.25 | Rückflug Einbau | Hans | Flavio
2019-06-06 | SDF | 80 | 1 | 538.3333 |  | Hans | Kevin
2019-06-07 | 1 | 35 | 1 | 278.75 | Flug 1 und 3 failed | Dave | Flavio
2019-06-08 | 2 | 66 | 1 | 448.5 | Flug 2 und 4 | Hans | Kevin
2019-06-12 | 3 | 63 | 1 | 429.25 | Flug 1 und 3 | Hans | Flavio
2019-06-13 | 4 | 83 | 1 | 557.5833 | Flug 6 und 8 | Hans | Kevin
2019-06-13 | 5 | 84 | 1 | 564 | Flug 11 und 13 | Hans | Kevin
2019-06-14 | 6 | 82 | 1 | 551.1667 | Flug 7 und 9 | Hans | Kevin
2019-06-14 | 7 | 44 | 1 | 307.3333 | Flug 15 | Hans | Kevin
2019-06-17 | 8 | 70 | 1 | 474.1667 | Flug 16 | Hans | Flavio
| 9 |  |  | 0
| 10 |  |  | 0
| 11 |  |  | 0
| 12 |  |  | 0
| 13 |  |  | 0
| 14 |  |  | 0
| 15 |  |  | 0
| 16 |  |  | 0
| 17 |  |  | 0
| 18 |  |  | 0
| 19 |  |  | 0
| 20 |  |  | 0
| M3 | 10 | 1 | 97.5
| M4 | 14 | 1 | 126.5
Total |  | 12.9333 |  | 5428.5
Berechnung Strafstunden
Bis jetzt | 27 | 11.7667 |  | 1066.3333
Verlängert | 37 | 11.7667 |  | 1766.3333
Rechnungen
Kaution |  | 0
Konstruktion Kevin |  | 106.9
Konstruktion Kevin |  | 299.75
Konstruktion Kevin |  | 560.05
Konstruktion Kevin |  | 33.85
Messinstrumentierung |  | 29.5
Mechaniker |  | 3354
ASFG Hans |  | 704.25
ASFG |  | 1911.7
ASFG |  | 3191.3
10191.3

## Timetable
Manoeuvre | CG | Duration | GND | SDF | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | Total
[5 empty] | Fwd | Aft | Fwd | Aft | Fwd | Aft | Fwd | Aft | Fwd | Aft | Fwd | Aft | Fwd | Fwd | Res. | Res. | Res. | Res. | Res. | Res. | Soll | Ist | Planned
|  |  | 2019-05-03 | 2019-05-04 | 2019-05-05 | 2019-05-05 | 2019-05-06 | 2019-05-06 | 2019-05-07 | 2019-05-07 | 2019-05-08 | 2019-05-08 | 2019-05-09 | 2019-05-09 | 2019-05-10 | 2019-05-10 | 2019-05-11 | 2019-05-11 | 2019-05-12 | 2019-05-12 | 2019-05-13 | 2019-05-13 | 2019-05-14 | 2019-05-14
Short Period #1 | Fwd | 3 |  | 2 | 1: 3; 3: 2; 5: 2; 7: 3; 9: 3; 11: 3; 13: 4; 14: 4 | 24 | 24 | 24
Short Period #1 | Aft | 3 |  |  | 2: 5; 4: 4; 6: 4; 8: 5; 10: 3; 12: 3 | 24 | 24 | 26
Short Period #2 | Fwd | 3 | [22 empty] | 4 | 4 | 4 | bar: 3; 5; 7; 11
Phugoid | Fwd | 5 |  | 2 | 1: 1; 3: 1; 5: 1; 7: 1; 9: 1; 11: 1; 13: 2 | 8 | 8 | 8
Phugoid | Aft | 5 |  |  | 2: 1; 4: 1; 6: 2; 8: 1; 10: 2; 12: 1 | 8 | 8 | 9
Pushover-pull-up | Fwd | 5 |  | 2 | [20 empty] | 2 | 2 | 2 | bar: 1; 7
Pushover-pull-up | Aft | 5 | [22 empty] | 2 | 2 | 3 | bar: 4; 10
Level turn | Fwd | 3 |  | 1 | [20 empty] | 4 | 4 | 5 | bar: 3; 5; 11; 14
Thrust variation | Fwd | 4 |  | 1 | [20 empty] | 4 | 4 | 4 | bar: 6; 8; 13 to 14
Bank-to-bank roll | Fwd | 3 |  | 1 | [20 empty] | 4 | 4 | 7 | bar: 1; 4; 7; 10
Dutch roll manoeuvre | Fwd | 3 |  | 1 | 1: 2; 3: 1; 5: 2; 7: 1; 9: 2; 11: 2; 13: 2 | 12 | 12 | 17
Dutch roll manoeuvre | Aft | 3 |  |  | 2: 2; 4: 2; 6: 2; 8: 2; 10: 2; 12: 2 | 12 | 12 | 9
Steady heading steady sideslip #1 | Fwd | 5 |  |  | 1: 1; 3: 1; 5: 1; 7: 1; 9: 1; 11: 1; 13: 2 | 8 | 8 | 10
Steady heading steady sideslip #2 | Fwd | 5 | [22 empty] | 4 | 4 | 4 | bar: 3; 7; 9; 14
T/O | Fwd | 7 | [22 empty] | 6 | 6 | 6 | bar: 1; 3; 5; 9; 11; 14
T/O | Aft | 7 | [22 empty] | 6 | 6 | 6 | bar: 2; 4; 6; 8; 10; 12
Landing | Fwd | 7 | [22 empty] | 6 | 6 | 7 | bar: 1; 3; 5; 7; 9; 11
Landing | Aft | 7 | [22 empty] | 6 | 6 | 5 | bar: 2; 4; 6; 8; 10; 12
Go around | Fwd | 7 |  |  | 14: 2 | 2 | 2 | 2
Spiral-Check | Fwd | 4 |  | 1 | 3: 2; 5: 1; 7: 1; 11: 1; 13: 2; 14: 1 | 8 | 8 | 8
Spiral-Check | Aft | 4 |  |  | 2: 1; 4: 1; 6: 1; 8: 2; 10: 1; 12: 2 | 8 | 8 | 9
Stall | Fwd | 5 |  | 1 | [20 empty] | 2 | 2 | 3 | bar: 5; 9
Stall | Aft | 5 | [22 empty] | 2 | 2 | 1 | bar: 2; 12
Total |  |  | 0 | 12 | 11 | 12 | 12 | 12 | 12 | 12 | 12 | 13 | 11 | 12 | 12 | 11 | 13 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 178 | 166
Time [min] |  |  | 0 | 48 | 47 | 49 | 52 | 49 | 51 | 50 | 49 | 52 | 49 | 51 | 49 | 47 | 50 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 12.3667
Planned (see Detailed) |  |  |  |  | 12 | 7 | 12 | 8 | 8 | 11 | 12 | 14 | 11 | 9 | 13 | 6 | 15 | 8
Note on AB3: ====== ID#AAAADLXwNN0 Autor (2019-07-04 12:04:12) see Detailed

## Matrix - Detailed
Manoeuvre ID | Rheinfolge | Flight ID | Manoeuvre | Completed | Usable | Duration [min] | CG | Altitude_s | Altitude_i | Flaps | Speed_s | Speed_i | Power_s | Power_i | Initial Input | Stick | 1st Step | 2nd Step | 3rd Step | 4th Step | 5th Step | 6th Step | 7th Step | Restrictions | Notes | Success Criteria
1 | 1 | 1 | Short period #1 | 1 |  | 3 | Fwd | Medium | 6500 ft | Up | Low | 70 | Medium | fly level | PUSH-PULL | free / fixed | Set configuration, A/C must keep attitude for 20s | Short PUSH-PULL-pulse on elevator, AOA change ~±3° | Bring yoke back to trim position | Wait until oscillation disapears | - | - | - | Do not exceed 111 kt | Avoid maintaining angle of attack | Several oscillations on lateral axis
2 | 2 | 1 | Short period #1 | 1 |  | 3 | Fwd | Medium | 6500 ft | Up | Low | 70 | Medium | fly level | PUSH-PULL | free / fixed | Set configuration, A/C must keep attitude for 20s | Short PUSH-PULL-pulse on elevator, AOA change ~±3° | Bring yoke back to trim position | Wait until oscillation disapears | - | - | - | Do not exceed 111 kt | Avoid maintaining angle of attack | Several oscillations on lateral axis
3 | 3 | 1 | Short period #1 | 1 |  | 3 | Fwd | Medium | 6500 ft | Up | Low | 70 | Medium | fly level | PULL-PUSH | free / fixed | Set configuration, A/C must keep attitude for 20s | Short PULL-PUSH-pulse on elevator, AOA change ~±3° | Bring yoke back to trim position | Wait until oscillation disapears | - | - | - | Do not exceed 111 kt | Avoid maintaining angle of attack | Several oscillations on lateral axis
4 | 4 | 3 | Short period #1 | 0 |  | 3 | Fwd | Medium | 6500 ft | Up | Low | 70 | Medium | fly level | PULL-PUSH | free / fixed | Set configuration, A/C must keep attitude for 20s | Short PULL-PUSH-pulse on elevator, AOA change ~±3° | Bring yoke back to trim position | Wait until oscillation disapears | - | - | - | Do not exceed 111 kt | Avoid maintaining angle of attack | Several oscillations on lateral axis
5 | 5 | 3 | Short period #1 | 1 | 0.5 | 3 | Fwd | Medium | 6500 ft | Up | Medium | 80 | Medium | fly level | PUSH-PULL | free / fixed | Set configuration, A/C must keep attitude for 20s | Short PUSH-PULL-pulse on elevator, AOA change ~±3° | Bring yoke back to trim position | Wait until oscillation disapears | - | - | - | Do not exceed 111 kt | Avoid maintaining angle of attack | Several oscillations on lateral axis
6 | 6 | 5 | Short period #1 | 0 |  | 3 | Fwd | Medium | 6500 ft | Up | Medium | 80 | Medium | fly level | PUSH-PULL | free / fixed | Set configuration, A/C must keep attitude for 20s | Short PUSH-PULL-pulse on elevator, AOA change ~±3° | Bring yoke back to trim position | Wait until oscillation disapears | - | - | - | Do not exceed 111 kt | Avoid maintaining angle of attack | Several oscillations on lateral axis
7 | 7 | 5 | Short period #1 | 0 |  | 3 | Fwd | Medium | 6500 ft | Up | Medium | 80 | Medium | fly level | PULL-PUSH | free / fixed | Set configuration, A/C must keep attitude for 20s | Short PULL-PUSH-pulse on elevator, AOA change ~±3° | Bring yoke back to trim position | Wait until oscillation disapears | - | - | - | Do not exceed 111 kt | Avoid maintaining angle of attack | Several oscillations on lateral axis
8 | 8 | 7 | Short period #1 | 1 |  | 3 | Fwd | Medium | 6500 ft | Up | Medium | 80 | Medium | fly level | PULL-PUSH | free / fixed | Set configuration, A/C must keep attitude for 20s | Short PULL-PUSH-pulse on elevator, AOA change ~±3° | Bring yoke back to trim position | Wait until oscillation disapears | - | - | - | Do not exceed 111 kt | Avoid maintaining angle of attack | Several oscillations on lateral axis
9 | 9 | 7 | Short period #1 | 1 |  | 3 | Fwd | Medium | 6500 ft | Up | High | 95 | Medium | fly level | PUSH-PULL | free / fixed | Set configuration, A/C must keep attitude for 20s | Short PUSH-PULL-pulse on elevator, AOA change ~±3° | Bring yoke back to trim position | Wait until oscillation disapears | - | - | - | Do not exceed 111 kt | Avoid maintaining angle of attack | Several oscillations on lateral axis
10 | 10 | 7 | Short period #1 | 1 |  | 3 | Fwd | Medium | 6500 ft | Up | High | 95 | Medium | fly level | PUSH-PULL | free / fixed | Set configuration, A/C must keep attitude for 20s | Short PUSH-PULL-pulse on elevator, AOA change ~±3° | Bring yoke back to trim position | Wait until oscillation disapears | - | - | - | Do not exceed 111 kt | Avoid maintaining angle of attack | Several oscillations on lateral axis
11 | 11 | 9 | Short period #1 | 1 |  | 3 | Fwd | Medium | 6500 ft | Up | High | 95 | Medium | fly level | PULL-PUSH | free / fixed | Set configuration, A/C must keep attitude for 20s | Short PULL-PUSH-pulse on elevator, AOA change ~±3° | Bring yoke back to trim position | Wait until oscillation disapears | - | - | - | Do not exceed 111 kt | Avoid maintaining angle of attack | Several oscillations on lateral axis
12 | 12 | 9 | Short period #1 | 1 |  | 3 | Fwd | Medium | 6500 ft | Up | High | 95 | Medium | fly level | PULL-PUSH | free / fixed | Set configuration, A/C must keep attitude for 20s | Short PULL-PUSH-pulse on elevator, AOA change ~±3° | Bring yoke back to trim position | Wait until oscillation disapears | - | - | - | Do not exceed 111 kt | Avoid maintaining angle of attack | Several oscillations on lateral axis
13 | 13 | 9 | Short period #1 | 1 |  | 3 | Fwd | High | 3500 ft | Up | Low | 70 | Medium | fly level | PUSH-PULL | free / fixed | Set configuration, A/C must keep attitude for 20s | Short PUSH-PULL-pulse on elevator, AOA change ~±3° | Bring yoke back to trim position | Wait until oscillation disapears | - | - | - | Do not exceed 111 kt | Avoid maintaining angle of attack | Several oscillations on lateral axis
14 | 14 | 11 | Short period #1 | 1 |  | 3 | Fwd | High | 3500 ft | Up | Low | 70 | Medium | fly level | PUSH-PULL | free / fixed | Set configuration, A/C must keep attitude for 20s | Short PUSH-PULL-pulse on elevator, AOA change ~±3° | Bring yoke back to trim position | Wait until oscillation disapears | - | - | - | Do not exceed 111 kt | Avoid maintaining angle of attack | Several oscillations on lateral axis
15 | 15 | 11 | Short period #1 | 1 |  | 3 | Fwd | High | 3500 ft | Up | Low | 70 | Medium | fly level | PULL-PUSH | free / fixed | Set configuration, A/C must keep attitude for 20s | Short PULL-PUSH-pulse on elevator, AOA change ~±3° | Bring yoke back to trim position | Wait until oscillation disapears | - | - | - | Do not exceed 111 kt | Avoid maintaining angle of attack | Several oscillations on lateral axis
16 | 16 | 11 | Short period #1 | 1 |  | 3 | Fwd | High | 3500 ft | Up | Low | 70 | Medium | fly level | PULL-PUSH | free / fixed | Set configuration, A/C must keep attitude for 20s | Short PULL-PUSH-pulse on elevator, AOA change ~±3° | Bring yoke back to trim position | Wait until oscillation disapears | - | - | - | Do not exceed 111 kt | Avoid maintaining angle of attack | Several oscillations on lateral axis
17 | 17 | 13 | Short period #1 | 1 |  | 3 | Fwd | High | 3500 ft | Up | Medium | 80 | Medium | fly level | PUSH-PULL | free / fixed | Set configuration, A/C must keep attitude for 20s | Short PUSH-PULL-pulse on elevator, AOA change ~±3° | Bring yoke back to trim position | Wait until oscillation disapears | - | - | - | Do not exceed 111 kt | Avoid maintaining angle of attack | Several oscillations on lateral axis
18 | 18 | 13 | Short period #1 | 1 |  | 3 | Fwd | High | 3500 ft | Up | Medium | 80 | Medium | fly level | PUSH-PULL | free / fixed | Set configuration, A/C must keep attitude for 20s | Short PUSH-PULL-pulse on elevator, AOA change ~±3° | Bring yoke back to trim position | Wait until oscillation disapears | - | - | - | Do not exceed 111 kt | Avoid maintaining angle of attack | Several oscillations on lateral axis
19 | 19 | 13 | Short period #1 | 1 |  | 3 | Fwd | High | 3500 ft | Up | Medium | 80 | Medium | fly level | PULL-PUSH | free / fixed | Set configuration, A/C must keep attitude for 20s | Short PULL-PUSH-pulse on elevator, AOA change ~±3° | Bring yoke back to trim position | Wait until oscillation disapears | - | - | - | Do not exceed 111 kt | Avoid maintaining angle of attack | Several oscillations on lateral axis
20 | 20 | 13 | Short period #1 | 1 |  | 3 | Fwd | High | 3500 ft | Up | Medium | 80 | Medium | fly level | PULL-PUSH | free / fixed | Set configuration, A/C must keep attitude for 20s | Short PULL-PUSH-pulse on elevator, AOA change ~±3° | Bring yoke back to trim position | Wait until oscillation disapears | - | - | - | Do not exceed 111 kt | Avoid maintaining angle of attack | Several oscillations on lateral axis
21 | 21 | 14 | Short period #1 | 0 |  | 3 | Fwd | High | 3500 ft | Up | High | 95 | Medium | fly level | PUSH-PULL | free / fixed | Set configuration, A/C must keep attitude for 20s | Short PUSH-PULL-pulse on elevator, AOA change ~±3° | Bring yoke back to trim position | Wait until oscillation disapears | - | - | - | Do not exceed 111 kt | Avoid maintaining angle of attack | Several oscillations on lateral axis
22 | 22 | 14 | Short period #1 | 0 |  | 3 | Fwd | High | 3500 ft | Up | High | 95 | Medium | fly level | PUSH-PULL | free / fixed | Set configuration, A/C must keep attitude for 20s | Short PUSH-PULL-pulse on elevator, AOA change ~±3° | Bring yoke back to trim position | Wait until oscillation disapears | - | - | - | Do not exceed 111 kt | Avoid maintaining angle of attack | Several oscillations on lateral axis
23 | 23 | 14 | Short period #1 | 0 |  | 3 | Fwd | High | 3500 ft | Up | High | 95 | Medium | fly level | PULL-PUSH | free / fixed | Set configuration, A/C must keep attitude for 20s | Short PULL-PUSH-pulse on elevator, AOA change ~±3° | Bring yoke back to trim position | Wait until oscillation disapears | - | - | - | Do not exceed 111 kt | Avoid maintaining angle of attack | Several oscillations on lateral axis
24 | 24 | 14 | Short period #1 | 0 |  | 3 | Fwd | High | 3500 ft | Up | High | 95 | Medium | fly level | PULL-PUSH | free / fixed | Set configuration, A/C must keep attitude for 20s | Short PULL-PUSH-pulse on elevator, AOA change ~±3° | Bring yoke back to trim position | Wait until oscillation disapears | - | - | - | Do not exceed 111 kt | Avoid maintaining angle of attack | Several oscillations on lateral axis
25 | 25 | 2 | Short period #1 | 0 |  | 3 | Aft | Medium | 6500 ft | Up | Low | 70 | Medium | fly level | PUSH-PULL | free / fixed | Set configuration, A/C must keep attitude for 20s | Short PUSH-PULL-pulse on elevator, AOA change ~±3° | Bring yoke back to trim position | Wait until oscillation disapears | - | - | - | Do not exceed 111 kt | Avoid maintaining angle of attack | Several oscillations on lateral axis
26 | 26 | 2 | Short period #1 | 0 |  | 3 | Aft | Medium | 6500 ft | Up | Low | 70 | Medium | fly level | PUSH-PULL | free / fixed | Set configuration, A/C must keep attitude for 20s | Short PUSH-PULL-pulse on elevator, AOA change ~±3° | Bring yoke back to trim position | Wait until oscillation disapears | - | - | - | Do not exceed 111 kt | Avoid maintaining angle of attack | Several oscillations on lateral axis
27 | 27 | 2 | Short period #1 | 0 |  | 3 | Aft | Medium | 6500 ft | Up | Low | 70 | Medium | fly level | PUSH-PULL | free / fixed | Set configuration, A/C must keep attitude for 20s | Short PUSH-PULL-pulse on elevator, AOA change ~±3° | Bring yoke back to trim position | Wait until oscillation disapears | - | - | - | Do not exceed 111 kt | Avoid maintaining angle of attack | Several oscillations on lateral axis
28 | 28 | 2 | Short period #1 | 0 |  | 3 | Aft | Medium | 6500 ft | Up | Low | 70 | Medium | fly level | PUSH-PULL | free / fixed | Set configuration, A/C must keep attitude for 20s | Short PUSH-PULL-pulse on elevator, AOA change ~±3° | Bring yoke back to trim position | Wait until oscillation disapears | - | - | - | Do not exceed 111 kt | Avoid maintaining angle of attack | Several oscillations on lateral axis
29 | 29 | 17 | Short period #1 | 0 |  | 3 | Aft | Medium | 6500 ft | Up | Medium | 80 | Medium | fly level | PULL-PUSH | free / fixed | Set configuration, A/C must keep attitude for 20s | Short PULL-PUSH-pulse on elevator, AOA change ~±3° | Bring yoke back to trim position | Wait until oscillation disapears | - | - | - | Do not exceed 111 kt | Avoid maintaining angle of attack | Several oscillations on lateral axis
30 | 30 | 17 | Short period #1 | 1 |  | 3 | Aft | Medium | 6500 ft | Up | Medium | 80 | Low | descent | PULL-PUSH | free / fixed | Set configuration, A/C must keep attitude for 20s | Short PULL-PUSH-pulse on elevator, AOA change ~±3° | Bring yoke back to trim position | Wait until oscillation disapears | - | - | - | Do not exceed 111 kt | Avoid maintaining angle of attack | Several oscillations on lateral axis
31 | 31 | 17 | Short period #1 | 1 |  | 3 | Aft | Medium | 6500 ft | Up | Medium | 80 | Max | descent | PUSH-PULL | free / fixed | Set configuration, A/C must keep attitude for 20s | Short PUSH-PULL-pulse on elevator, AOA change ~±3° | Bring yoke back to trim position | Wait until oscillation disapears | - | - | - | Do not exceed 111 kt | Avoid maintaining angle of attack | Several oscillations on lateral axis
32 | 32 | 17 | Short period #1 | 0 |  | 3 | Aft | Medium | 6500 ft | Up | Medium | 80 | Medium | fly level | PUSH-PULL | free / fixed | Set configuration, A/C must keep attitude for 20s | Short PUSH-PULL-pulse on elevator, AOA change ~±3° | Bring yoke back to trim position | Wait until oscillation disapears | - | - | - | Do not exceed 111 kt | Avoid maintaining angle of attack | Several oscillations on lateral axis
33 | 33 | 4 | Short period #1 | 1 |  | 3 | Aft | Medium | 6500 ft | Up | High | 95 | Medium | fly level | PULL-PUSH | free / fixed | Set configuration, A/C must keep attitude for 20s | Short PULL-PUSH-pulse on elevator, AOA change ~±3° | Bring yoke back to trim position | Wait until oscillation disapears | - | - | - | Do not exceed 111 kt | Avoid maintaining angle of attack | Several oscillations on lateral axis
34 | 34 | 6 | Short period #1 | 1 |  | 3 | Aft | Medium | 6500 ft | Up | High | 95 | Medium | fly level | PULL-PUSH | free / fixed | Set configuration, A/C must keep attitude for 20s | Short PULL-PUSH-pulse on elevator, AOA change ~±3° | Bring yoke back to trim position | Wait until oscillation disapears | - | - | - | Do not exceed 111 kt | Avoid maintaining angle of attack | Several oscillations on lateral axis
35 | 35 | 6 | Short period #1 | 1 |  | 3 | Aft | Medium | 6500 ft | Up | High | 95 | Medium | fly level | PUSH-PULL | free / fixed | Set configuration, A/C must keep attitude for 20s | Short PUSH-PULL-pulse on elevator, AOA change ~±3° | Bring yoke back to trim position | Wait until oscillation disapears | - | - | - | Do not exceed 111 kt | Avoid maintaining angle of attack | Several oscillations on lateral axis
36 | 36 | 6 | Short period #1 | 1 |  | 3 | Aft | Medium | 6500 ft | Up | High | 95 | Medium | fly level | PUSH-PULL | free / fixed | Set configuration, A/C must keep attitude for 20s | Short PUSH-PULL-pulse on elevator, AOA change ~±3° | Bring yoke back to trim position | Wait until oscillation disapears | - | - | - | Do not exceed 111 kt | Avoid maintaining angle of attack | Several oscillations on lateral axis
37 | 37 | 6 | Short period #1 | 1 |  | 3 | Aft | High | 3500 ft | Up | Low | 70 | Medium | fly level | PULL-PUSH | free / fixed | Set configuration, A/C must keep attitude for 20s | Short PULL-PUSH-pulse on elevator, AOA change ~±3° | Bring yoke back to trim position | Wait until oscillation disapears | - | - | - | Do not exceed 111 kt | Avoid maintaining angle of attack | Several oscillations on lateral axis
38 | 38 | 8 | Short period #1 | 1 |  | 3 | Aft | High | 3500 ft | Up | Low | 70 | Medium | fly level | PULL-PUSH | free / fixed | Set configuration, A/C must keep attitude for 20s | Short PULL-PUSH-pulse on elevator, AOA change ~±3° | Bring yoke back to trim position | Wait until oscillation disapears | - | - | - | Do not exceed 111 kt | Avoid maintaining angle of attack | Several oscillations on lateral axis
39 | 39 | 8 | Short period #1 | 1 |  | 3 | Aft | High | 3500 ft | Up | Low | 70 | Medium | fly level | PUSH-PULL | free / fixed | Set configuration, A/C must keep attitude for 20s | Short PUSH-PULL-pulse on elevator, AOA change ~±3° | Bring yoke back to trim position | Wait until oscillation disapears | - | - | - | Do not exceed 111 kt | Avoid maintaining angle of attack | Several oscillations on lateral axis
401 | 40 | 8 | Short period #1 | 1 |  | 3 | Aft | High | 3500 ft | Up | Low | 70 | Medium | fly level | PUSH-PULL | free / fixed | Set configuration, A/C must keep attitude for 20s | Short PUSH-PULL-pulse on elevator, AOA change ~±3° | Bring yoke back to trim position | Wait until oscillation disapears | - | - | - | Do not exceed 111 kt | Avoid maintaining angle of attack | Several oscillations on lateral axis
402 | 40 | 8 | Short period #1 | 1 |  | 3 | Aft | High | 3500 ft | Up | Low | 70 | Medium | fly level | PUSH-PULL | free / fixed | Set configuration, A/C must keep attitude for 20s | Short PUSH-PULL-pulse on elevator, AOA change ~±3° | Bring yoke back to trim position | Wait until oscillation disapears | - | - | - | Do not exceed 111 kt | Avoid maintaining angle of attack | Several oscillations on lateral axis
41 | 41 | 8 | Short period #1 | 1 |  | 3 | Aft | High | 3500 ft | Up | Medium | 80 | Medium | fly level | PULL-PUSH | free / fixed | Set configuration, A/C must keep attitude for 20s | Short PULL-PUSH-pulse on elevator, AOA change ~±3° | Bring yoke back to trim position | Wait until oscillation disapears | - | - | - | Do not exceed 111 kt | Avoid maintaining angle of attack | Several oscillations on lateral axis
42 | 42 | 8 | Short period #1 | 1 |  | 3 | Aft | High | 3500 ft | Up | Medium | 80 | Medium | fly level | PULL-PUSH | free / fixed | Set configuration, A/C must keep attitude for 20s | Short PULL-PUSH-pulse on elevator, AOA change ~±3° | Bring yoke back to trim position | Wait until oscillation disapears | - | - | - | Do not exceed 111 kt | Avoid maintaining angle of attack | Several oscillations on lateral axis
43 | 43 | 10 | Short period #1 | 0 |  | 3 | Aft | High | 3500 ft | Up | Medium | 80 | Medium | fly level | PUSH-PULL | free / fixed | Set configuration, A/C must keep attitude for 20s | Short PUSH-PULL-pulse on elevator, AOA change ~±3° | Bring yoke back to trim position | Wait until oscillation disapears | - | - | - | Do not exceed 111 kt | Avoid maintaining angle of attack | Several oscillations on lateral axis
44 | 44 | 10 | Short period #1 | 0 |  | 3 | Aft | High | 3500 ft | Up | Medium | 80 | Medium | fly level | PUSH-PULL | free / fixed | Set configuration, A/C must keep attitude for 20s | Short PUSH-PULL-pulse on elevator, AOA change ~±3° | Bring yoke back to trim position | Wait until oscillation disapears | - | - | - | Do not exceed 111 kt | Avoid maintaining angle of attack | Several oscillations on lateral axis
45 | 45 | 10 | Short period #1 | 0 |  | 3 | Aft | High | 3500 ft | Up | High | 95 | Medium | fly level | PULL-PUSH | free / fixed | Set configuration, A/C must keep attitude for 20s | Short PULL-PUSH-pulse on elevator, AOA change ~±3° | Bring yoke back to trim position | Wait until oscillation disapears | - | - | - | Do not exceed 111 kt | Avoid maintaining angle of attack | Several oscillations on lateral axis
46 | 46 | 17 | Short period #1 | 0 |  | 3 | Aft | High | 3500 ft | Up | High | 95 | Medium | fly level | PULL-PUSH | free / fixed | Set configuration, A/C must keep attitude for 20s | Short PULL-PUSH-pulse on elevator, AOA change ~±3° | Bring yoke back to trim position | Wait until oscillation disapears | - | - | - | Do not exceed 111 kt | Avoid maintaining angle of attack | Several oscillations on lateral axis
47 | 47 | 17 | Short period #1 | 0 |  | 3 | Aft | High | 3500 ft | Up | High | 95 | Medium | fly level | PUSH-PULL | free / fixed | Set configuration, A/C must keep attitude for 20s | Short PUSH-PULL-pulse on elevator, AOA change ~±3° | Bring yoke back to trim position | Wait until oscillation disapears | - | - | - | Do not exceed 111 kt | Avoid maintaining angle of attack | Several oscillations on lateral axis
48 | 48 | 12 | Short period #1 | 0 |  | 3 | Aft | High | 3500 ft | Up | High | 95 | Medium | fly level | PUSH-PULL | free / fixed | Set configuration, A/C must keep attitude for 20s | Short PUSH-PULL-pulse on elevator, AOA change ~±3° | Bring yoke back to trim position | Wait until oscillation disapears | - | - | - | Do not exceed 111 kt | Avoid maintaining angle of attack | Several oscillations on lateral axis
49 | 49 | 15 | Short period #2 | 1 |  | 3 | Fwd | Medium | 6500 ft | Up | Medium | 80 | Low | descent | PUSH-PULL | free / fixed | Set configuration, A/C must keep attitude for 20s | Short PUSH-PULL-pulse on elevator, AOA change ~±3° | Bring yoke back to trim position | Wait until oscillation disapears | - | - | - | Do not exceed 111 kt | Avoid maintaining angle of attack | Several oscillations on lateral axis
50 | 50 | 15 | Short period #2 | 1 |  | 3 | Fwd | Medium | 6500 ft | Up | Medium | 80 | Low | descent | PUSH-PULL | free / fixed | Set configuration, A/C must keep attitude for 20s | Short PUSH-PULL-pulse on elevator, AOA change ~±3° | Bring yoke back to trim position | Wait until oscillation disapears | - | - | - | Do not exceed 111 kt | Avoid maintaining angle of attack | Several oscillations on lateral axis
51 | 51 | 7 | Short period #2 | 1 |  | 3 | Fwd | Medium | 6500 ft | Up | Medium | 80 | Max | descent | PUSH-PULL | free / fixed | Set configuration, A/C must keep attitude for 20s | Short PUSH-PULL-pulse on elevator, AOA change ~±3° | Bring yoke back to trim position | Wait until oscillation disapears | - | - | - | Do not exceed 111 kt | Avoid maintaining angle of attack | Several oscillations on lateral axis
52 | 52 | 11 | Short period #2 | 1 |  | 3 | Fwd | Medium | 6500 ft | Up | Medium | 80 | Max | descent | PUSH-PULL | free / fixed | Set configuration, A/C must keep attitude for 20s | Short PUSH-PULL-pulse on elevator, AOA change ~±3° | Bring yoke back to trim position | Wait until oscillation disapears | - | - | - | Do not exceed 111 kt | Avoid maintaining angle of attack | Several oscillations on lateral axis
53 | 53 | 1 | Phugoid | 1 | 1 | 5 | Fwd | Medium | 6500 ft | Up | Medium | 80 | Medium | fly level | PUSH | free | Set configuration, A/C must keep attitude for 20s | PUSH Elevator until IAS 92 | Wait at least for 2 periods, then abort to level flight | - | - | - | - | Do not exceed 111 kt | If possible, three full cycles | Several oscillations on lateral axis
54 | 54 | 3 | Phugoid | 1 | 0.5 | 5 | Fwd | Medium | 6500 ft | Up | Medium | 80 | Medium | fly level | PUSH | free | Set configuration, A/C must keep attitude for 20s | PUSH Elevator until IAS 92 | Wait at least for 2 periods, then abort to level flight | - | - | - | - | Do not exceed 111 kt | If possible, three full cycles | Several oscillations on lateral axis
55 | 55 | 5 | Phugoid | 1 |  | 5 | Fwd | Medium | 6500 ft | Up | Medium | 80 | Medium | fly level | PULL | free | Set configuration, A/C must keep attitude for 20s | PULL Elevator until IAS 68 | Wait at least for 2 periods, then abort to level flight | - | - | - | - | Do not exceed 111 kt | If possible, three full cycles | Several oscillations on lateral axis
56 | 56 | 7 | Phugoid | 1 | 1 | 5 | Fwd | Medium | 6500 ft | Up | Medium | 80 | Medium | fly level | PULL | free | Set configuration, A/C must keep attitude for 20s | PULL Elevator until IAS 68 | Wait at least for 2 periods, then abort to level flight | - | - | - | - | Do not exceed 111 kt | If possible, three full cycles | Several oscillations on lateral axis
57 | 57 | 9 | Phugoid | 1 | 1 | 5 | Fwd | High | 3500 ft | Up | Medium | 80 | Medium | fly level | PUSH | free | Set configuration, A/C must keep attitude for 20s | PUSH Elevator until IAS 92 | Wait at least for 2 periods, then abort to level flight | - | - | - | - | Do not exceed 111 kt | If possible, three full cycles | Several oscillations on lateral axis
58 | 58 | 11 | Phugoid | 1 | 1 | 5 | Fwd | High | 3500 ft | Up | Medium | 80 | Medium | fly level | PUSH | free | Set configuration, A/C must keep attitude for 20s | PUSH Elevator until IAS 92 | Wait at least for 2 periods, then abort to level flight | - | - | - | - | Do not exceed 111 kt | If possible, three full cycles | Several oscillations on lateral axis
59 | 59 | 13 | Phugoid | 1 | 0.9 | 5 | Fwd | High | 3500 ft | Up | Medium | 80 | Medium | fly level | PULL | free | Set configuration, A/C must keep attitude for 20s | PULL Elevator until IAS 68 | Wait at least for 2 periods, then abort to level flight | - | - | - | - | Do not exceed 111 kt | If possible, three full cycles | Several oscillations on lateral axis
60 | 60 | 13 | Phugoid | 1 | 0.9 | 5 | Fwd | High | 3500 ft | Up | Medium | 80 | Medium | fly level | PULL | free | Set configuration, A/C must keep attitude for 20s | PULL Elevator until IAS 68 | Wait at least for 2 periods, then abort to level flight | - | - | - | - | Do not exceed 111 kt | If possible, three full cycles | Several oscillations on lateral axis
61 | 61 | 2 | Phugoid | 0 |  | 5 | Aft | Medium | 6500 ft | Up | Medium | 80 | Medium | fly level | PUSH | free | Set configuration, A/C must keep attitude for 20s | PUSH Elevator until IAS 92 | Wait at least for 2 periods, then abort to level flight | - | - | - | - | Do not exceed 111 kt | If possible, three full cycles | Several oscillations on lateral axis
62 | 62 | 17 | Phugoid | 0 |  | 5 | Aft | Medium | 6500 ft | Up | Medium | 80 | Medium | fly level | PUSH | free | Set configuration, A/C must keep attitude for 20s | PUSH Elevator until IAS 92 | Wait at least for 2 periods, then abort to level flight | - | - | - | - | Do not exceed 111 kt | If possible, three full cycles | Several oscillations on lateral axis
63 | 63 | 6 | Phugoid | 1 | 1 | 5 | Aft | Medium | 6500 ft | Up | Medium | 80 | Medium | fly level | PULL | free | Set configuration, A/C must keep attitude for 20s | PULL Elevator until IAS 68 | Wait at least for 2 periods, then abort to level flight | - | - | - | - | Do not exceed 111 kt | If possible, three full cycles | Several oscillations on lateral axis
64 | 64 | 6 | Phugoid | 1 | 1 | 5 | Aft | Medium | 6500 ft | Up | Medium | 80 | Medium | fly level | PULL | free | Set configuration, A/C must keep attitude for 20s | PULL Elevator until IAS 68 | Wait at least for 2 periods, then abort to level flight | - | - | - | - | Do not exceed 111 kt | If possible, three full cycles | Several oscillations on lateral axis
65 | 65 | 8 | Phugoid | 1 | 0 | 5 | Aft | High | 3500 ft | Up | Medium | 80 | Medium | fly level | PUSH | free | Set configuration, A/C must keep attitude for 20s | PUSH Elevator until IAS 92 | Wait at least for 2 periods, then abort to level flight | - | - | - | - | Do not exceed 111 kt | If possible, three full cycles | Several oscillations on lateral axis
66 | 66 | 17 | Phugoid | 1 | 1 | 5 | Aft | High | 3500 ft | Up | Medium | 80 | Medium | fly level | PUSH | free | Set configuration, A/C must keep attitude for 20s | PUSH Elevator until IAS 92 | Wait at least for 2 periods, then abort to level flight | - | - | - | - | Do not exceed 111 kt | If possible, three full cycles | Several oscillations on lateral axis
67 | 67 | 17 | Phugoid | 1 | 0 | 5 | Aft | High | 3500 ft | Up | Medium | 80 | Medium | fly level | PULL | free | Set configuration, A/C must keep attitude for 20s | PULL Elevator until IAS 68 | Wait at least for 2 periods, then abort to level flight | - | - | - | - | Do not exceed 111 kt | If possible, three full cycles | Several oscillations on lateral axis
68 | 68 | 12 | Phugoid | 0 |  | 5 | Aft | High | 3500 ft | Up | Medium | 80 | Medium | fly level | PULL | free | Set configuration, A/C must keep attitude for 20s | PULL Elevator until IAS 68 | Wait at least for 2 periods, then abort to level flight | - | - | - | - | Do not exceed 111 kt | If possible, three full cycles | Several oscillations on lateral axis
69 | 69 | 1 | Pushover-pull-up | 0 |  | 5 | Fwd | Medium | 6500 ft | Up | Medium | 80 | Medium | fly level | PUSH | free / fixed | Set configuration, A/C must keep attitude for 20s | Slowly and continuously push stick until IAS 92 | Slowly and continuously pull stick until above IAS 48 | Push stick slowly and return to trim condition | - | - | - | Do not exceed 111 kt | Constant power | Smooth/continuous change in IAS
70 | 70 | 7 | Pushover-pull-up | 0 |  | 5 | Fwd | Medium | 6500 ft | Up | Medium | 80 | Medium | fly level | PUSH | free / fixed | Set configuration, A/C must keep attitude for 20s | Slowly and continuously push stick until IAS 92 | Slowly and continuously pull stick until above IAS 48 | Push stick slowly and return to trim condition | - | - | - | Do not exceed 111 kt | Constant power | Smooth/continuous change in IAS
71 | 71 | 4 | Pushover-pull-up | 0 |  | 5 | Aft | Medium | 6500 ft | Up | Medium | 80 | Medium | fly level | PUSH | free / fixed | Set configuration, A/C must keep attitude for 20s | Slowly and continuously push stick until IAS 92 | Slowly and continuously pull stick until above IAS 48 | Push stick slowly and return to trim condition | - | - | - | Do not exceed 111 kt | Constant power | Smooth/continuous change in IAS
72 | 72 | 10 | Pushover-pull-up | 0 |  | 5 | Aft | Medium | 6500 ft | Up | Medium | 80 | Medium | fly level | PUSH | free / fixed | Set configuration, A/C must keep attitude for 20s | Slowly and continuously push stick until IAS 92 | Slowly and continuously pull stick until above IAS 48 | Push stick slowly and return to trim condition | - | - | - | Do not exceed 111 kt | Constant power | Smooth/continuous change in IAS
73 | 73 | 3 | Level turn | 1 |  | 3 | Fwd | Medium | 6500 ft | Up | Medium | 80 | Medium | fly level | LEFT | free / fixed | Set configuration, A/C must keep attitude for 20s | Bank LEFT (10 deg/s) until 45 deg reached | Keep angle for 15s | Bank RIGHT (10 deg/s) until 45 deg reached | Keep angle for 15s | Return to wings-level trim condition | - | Do not exceed 111 kt | Hold altitude with additional power | Undisturbed
74 | 74 | 16 | Level turn | 1 |  | 3 | Fwd | Medium | 6500 ft | Up | Medium | 80 | Medium | fly level | LEFT | free / fixed | Set configuration, A/C must keep attitude for 20s | Bank LEFT (10 deg/s) until 45 deg reached | Keep angle for 15s | Bank RIGHT (10 deg/s) until 45 deg reached | Keep angle for 15s | Return to wings-level trim condition | - | Do not exceed 111 kt | Hold altitude with additional power | Undisturbed
751 | 75 | 11 | Level turn | 1 |  | 3 | Fwd | Medium | 6500 ft | Up | Medium | 80 | Medium | fly level | RIGHT | free / fixed | Set configuration, A/C must keep attitude for 20s | Bank RIGHT (10 deg/s) until 45 deg reached | Keep angle for 15s | Bank LEFT (10 deg/s) until 45 deg reached | Keep angle for 15s | Return to wings-level trim condition | - | Do not exceed 111 kt | Hold altitude with additional power | Undisturbed
752 | 75 | 11 | Level turn | 1 |  | 3 | Fwd | Medium | 6500 ft | Up | Medium | 80 | Medium | fly level | RIGHT | free / fixed | Set configuration, A/C must keep attitude for 20s | Bank RIGHT (10 deg/s) until 45 deg reached | Keep angle for 15s | Bank LEFT (10 deg/s) until 45 deg reached | Keep angle for 15s | Return to wings-level trim condition | - | Do not exceed 111 kt | Hold altitude with additional power | Undisturbed
76 | 76 | 16 | Level turn | 1 |  | 3 | Fwd | Medium | 6500 ft | Up | Medium | 80 | Medium | fly level | RIGHT | free / fixed | Set configuration, A/C must keep attitude for 20s | Bank RIGHT (10 deg/s) until 45 deg reached | Keep angle for 15s | Bank LEFT (10 deg/s) until 45 deg reached | Keep angle for 15s | Return to wings-level trim condition | - | Do not exceed 111 kt | Hold altitude with additional power | Undisturbed
77 | 77 | 6 | Thrust variation | 0 |  | 4 | Fwd | Low | 5500 ft | Up | Medium | 80 | Medium | fly level | Single | free / fixed | Set configuration, A/C must keep attitude for 20s | Remove hands from yoke and feet from pedals | Push power rapidly to maxiumum | Wait until A/C stabilized again | Pull power lever rapidly to idle | Wait until A/C stabilized again | Return to trim condition | Do not exceed 111 kt | Engine must not over-rev | Undisturbed
78 | 78 | 8 | Thrust variation | 0 |  | 4 | Fwd | Low | 5500 ft | Up | Medium | 80 | Medium | fly level | Single | free / fixed | Set configuration, A/C must keep attitude for 20s | Remove hands from yoke and feet from pedals | Push power rapidly to maxiumum | Wait until A/C stabilized again | Pull power lever rapidly to idle | Wait until A/C stabilized again | Return to trim condition | Do not exceed 111 kt | Engine must not over-rev | Undisturbed
79 | 79 | 13 | Thrust variation | 0 |  | 4 | Fwd | High | 3500 ft | Up | Medium | 80 | Medium | fly level | Single | free / fixed | Set configuration, A/C must keep attitude for 20s | Remove hands from yoke and feet from pedals | Push power rapidly to maxiumum | Wait until A/C stabilized again | Pull power lever rapidly to idle | Wait until A/C stabilized again | Return to trim condition | Do not exceed 111 kt | Engine must not over-rev | Undisturbed
80 | 80 | 14 | Thrust variation | 0 |  | 4 | Fwd | High | 3500 ft | Up | Medium | 80 | Medium | fly level | Single | free / fixed | Set configuration, A/C must keep attitude for 20s | Remove hands from yoke and feet from pedals | Push power rapidly to maxiumum | Wait until A/C stabilized again | Pull power lever rapidly to idle | Wait until A/C stabilized again | Return to trim condition | Do not exceed 111 kt | Engine must not over-rev | Undisturbed
811 | 81 | 1 | Bank-to-bank roll | 0 |  | 3 | Fwd | Medium | 6500 ft | Up | Medium | 80 | Medium | fly level | LEFT | free / fixed | Set configuration, A/C must keep attitude for 20s | Sharp input to bank LEFT until 30 deg reached | Keep angle for 10s | Sharp input to bank RIGHT until 30 deg reached | Keep angle for 10 seconds | Return to wings-level trim condition | - | Do not exceed 111 kt | - | Undisturbed
812 | 81 | 1 | Bank-to-bank roll | 1 |  | 3 | Fwd | Medium | 6500 ft | Up | Medium | 80 | Medium | fly level | LEFT | free / fixed | Set configuration, A/C must keep attitude for 20s | Sharp input to bank LEFT until 30 deg reached | Keep angle for 10s | Sharp input to bank RIGHT until 30 deg reached | Keep angle for 10 seconds | Return to wings-level trim condition | - | Do not exceed 111 kt | - | Undisturbed
821 | 82 | 4 | Bank-to-bank roll | 1 |  | 3 | Fwd | Medium | 6500 ft | Up | Medium | 80 | Medium | fly level | LEFT | free / fixed | Set configuration, A/C must keep attitude for 20s | Sharp input to bank LEFT until 30 deg reached | Keep angle for 10s | Sharp input to bank LEFT until 30 deg reached | Keep angle for 10 seconds | Return to wings-level trim condition | - | Do not exceed 111 kt | - | Undisturbed
822 | 82 | 4 | Bank-to-bank roll | 1 |  | 3 | Fwd | Medium | 6500 ft | Up | Medium | 80 | Medium | fly level | LEFT | free / fixed | Set configuration, A/C must keep attitude for 20s | Sharp input to bank LEFT until 30 deg reached | Keep angle for 10s | Sharp input to bank RIGHT until 30 deg reached | Keep angle for 10 seconds | Return to wings-level trim condition | - | Do not exceed 111 kt | - | Undisturbed
83 | 83 | 7 | Bank-to-bank roll | 1 |  | 3 | Fwd | Medium | 6500 ft | Up | Medium | 80 | Medium | fly level | RIGHT | free / fixed | Set configuration, A/C must keep attitude for 20s | Sharp input to bank RIGHT until 30 deg reached | Keep angle for 10s | Sharp input to bank RIGHT until 30 deg reached | Keep angle for 10 seconds | Return to wings-level trim condition | - | Do not exceed 111 kt | - | Undisturbed
841 | 84 | 10 | Bank-to-bank roll | 1 |  | 3 | Fwd | Medium | 6500 ft | Up | Medium | 80 | Medium | fly level | RIGHT | free / fixed | Set configuration, A/C must keep attitude for 20s | Sharp input to bank RIGHT until 30 deg reached | Keep angle for 10s | Sharp input to bank RIGHT until 30 deg reached | Keep angle for 10 seconds | Return to wings-level trim condition | - | Do not exceed 111 kt | - | Undisturbed
842 | 84 | 10 | Bank-to-bank roll | 1 |  | 3 | Fwd | Medium | 6500 ft | Up | Medium | 80 | Medium | fly level | RIGHT | free / fixed | Set configuration, A/C must keep attitude for 20s | Sharp input to bank RIGHT until 30 deg reached | Keep angle for 10s | Sharp input to bank LEFT until 30 deg reached | Keep angle for 10 seconds | Return to wings-level trim condition | - | Do not exceed 111 kt | - | Undisturbed
85 | 85 | 1 | Dutch roll manoeuvre | 1 | 0.5 | 3 | Fwd | Medium | 6500 ft | Up | Low | 70 | Medium | fly level | LEFT-RIGHT |  | Set configuration, A/C must keep attitude for 20s | Doublet input until ball about 1 off | Set pedals back to neutral | Wait until oscillation disapears | - | - | - | Do not exceed 111 kt | - | Several dutch roll oscillations
86 | 86 | 1 | Dutch roll manoeuvre | 1 |  | 3 | Fwd | Medium | 6500 ft | Up | Low | 70 | Medium | fly level | LEFT-RIGHT |  | Set configuration, A/C must keep attitude for 20s | Doublet input until ball about 1 off | Set pedals back to neutral | Wait until oscillation disapears | - | - | - | Do not exceed 111 kt | - | Several dutch roll oscillations
871 | 87 | 3 | Dutch roll manoeuvre | 1 |  | 3 | Fwd | Medium | 6500 ft | Up | Medium | 80 | Medium | fly level | LEFT-RIGHT |  | Set configuration, A/C must keep attitude for 20s | Doublet input until ball about 1 off | Set pedals back to neutral | Wait until oscillation disapears | - | - | - | Do not exceed 111 kt | - | Several dutch roll oscillations
872 | 87 | 3 | Dutch roll manoeuvre | 1 |  | 3 | Fwd | Medium | 6500 ft | Up | Medium | 80 | Medium | fly level | LEFT-RIGHT |  | Set configuration, A/C must keep attitude for 20s | Doublet input until ball about 1 off | Set pedals back to neutral | Wait until oscillation disapears | - | - | - | Do not exceed 111 kt | - | Several dutch roll oscillations
88 | 88 | 5 | Dutch roll manoeuvre | 1 | 0.5 | 3 | Fwd | Medium | 6500 ft | Up | Medium | 80 | Medium | fly level | LEFT-RIGHT |  | Set configuration, A/C must keep attitude for 20s | Doublet input until ball about 1 off | Set pedals back to neutral | Wait until oscillation disapears | - | - | - | Do not exceed 111 kt | - | Several dutch roll oscillations
89 | 89 | 17 | Dutch roll manoeuvre | 0 |  | 3 | Fwd | Medium | 6500 ft | Up | High | 95 | Medium | fly level | LEFT-RIGHT |  | Set configuration, A/C must keep attitude for 20s | Doublet input until ball about 1 off | Set pedals back to neutral | Wait until oscillation disapears | - | - | - | Do not exceed 111 kt | - | Several dutch roll oscillations
90 | 90 | 7 | Dutch roll manoeuvre | 1 |  | 3 | Fwd | Medium | 6500 ft | Up | High | 95 | Medium | fly level | LEFT-RIGHT |  | Set configuration, A/C must keep attitude for 20s | Doublet input until ball about 1 off | Set pedals back to neutral | Wait until oscillation disapears | - | - | - | Do not exceed 111 kt | - | Several dutch roll oscillations
91 | 91 | 9 | Dutch roll manoeuvre | 1 |  | 3 | Fwd | High | 3500 ft | Up | Low | 70 | Medium | fly level | LEFT-RIGHT |  | Set configuration, A/C must keep attitude for 20s | Doublet input until ball about 1 off | Set pedals back to neutral | Wait until oscillation disapears | - | - | - | Do not exceed 111 kt | - | Several dutch roll oscillations
92 | 92 | 9 | Dutch roll manoeuvre | 1 |  | 3 | Fwd | High | 3500 ft | Up | Low | 70 | Medium | fly level | LEFT-RIGHT |  | Set configuration, A/C must keep attitude for 20s | Doublet input until ball about 1 off | Set pedals back to neutral | Wait until oscillation disapears | - | - | - | Do not exceed 111 kt | - | Several dutch roll oscillations
93 | 93 | 11 | Dutch roll manoeuvre | 1 |  | 3 | Fwd | High | 3500 ft | Up | Medium | 80 | Medium | fly level | LEFT-RIGHT |  | Set configuration, A/C must keep attitude for 20s | Doublet input until ball about 1 off | Set pedals back to neutral | Wait until oscillation disapears | - | - | - | Do not exceed 111 kt | - | Several dutch roll oscillations
94 | 94 | 11 | Dutch roll manoeuvre | 1 |  | 3 | Fwd | High | 3500 ft | Up | Medium | 80 | Medium | fly level | LEFT-RIGHT |  | Set configuration, A/C must keep attitude for 20s | Doublet input until ball about 1 off | Set pedals back to neutral | Wait until oscillation disapears | - | - | - | Do not exceed 111 kt | - | Several dutch roll oscillations
95 | 95 | 13 | Dutch roll manoeuvre | 1 |  | 3 | Fwd | High | 3500 ft | Up | High | 95 | Medium | fly level | LEFT-RIGHT |  | Set configuration, A/C must keep attitude for 20s | Doublet input until ball about 1 off | Set pedals back to neutral | Wait until oscillation disapears | - | - | - | Do not exceed 111 kt | - | Several dutch roll oscillations
96 | 96 | 13 | Dutch roll manoeuvre | 1 |  | 3 | Fwd | High | 3500 ft | Up | High | 95 | Medium | fly level | LEFT-RIGHT |  | Set configuration, A/C must keep attitude for 20s | Doublet input until ball about 1 off | Set pedals back to neutral | Wait until oscillation disapears | - | - | - | Do not exceed 111 kt | - | Several dutch roll oscillations
97 | 97 | 16 | Dutch roll manoeuvre | 1 |  | 3 | Fwd | Medium | 6500 ft | Up | Medium | 80 | Low | descent | RIGHT-LEFT |  | Set configuration, A/C must keep attitude for 20s | Doublet input until ball about 1 off | Set pedals back to neutral | Wait until oscillation disapears | - | - | - | Do not exceed 111 kt | - | Several dutch roll oscillations
98 | 98 | 17 | Dutch roll manoeuvre | 0 |  | 3 | Aft | Medium | 6500 ft | Up | Low | 70 | Medium | fly level | LEFT-RIGHT |  | Set configuration, A/C must keep attitude for 20s | Doublet input until ball about 1 off | Set pedals back to neutral | Wait until oscillation disapears | - | - | - | Do not exceed 111 kt | - | Several dutch roll oscillations
99 | 99 | 16 | Dutch roll manoeuvre | 1 |  | 3 | Fwd | Medium | 6500 ft | Up | Medium | 80 | Low | descent | RIGHT-LEFT |  | Set configuration, A/C must keep attitude for 20s | Doublet input until ball about 1 off | Set pedals back to neutral | Wait until oscillation disapears | - | - | - | Do not exceed 111 kt | - | Several dutch roll oscillations
100 | 100 | 4 | Dutch roll manoeuvre | 0 |  | 3 | Aft | Medium | 6500 ft | Up | Medium | 80 | Medium | fly level | LEFT-RIGHT |  | Set configuration, A/C must keep attitude for 20s | Doublet input until ball about 1 off | Set pedals back to neutral | Wait until oscillation disapears | - | - | - | Do not exceed 111 kt | - | Several dutch roll oscillations
101 | 101 | 6 | Dutch roll manoeuvre | 1 |  | 3 | Aft | Medium | 6500 ft | Up | High | 95 | Medium | fly level | LEFT-RIGHT |  | Set configuration, A/C must keep attitude for 20s | Doublet input until ball about 1 off | Set pedals back to neutral | Wait until oscillation disapears | - | - | - | Do not exceed 111 kt | - | Several dutch roll oscillations
102 | 102 | 6 | Dutch roll manoeuvre | 1 |  | 3 | Aft | Medium | 6500 ft | Up | High | 95 | Medium | fly level | LEFT-RIGHT |  | Set configuration, A/C must keep attitude for 20s | Doublet input until ball about 1 off | Set pedals back to neutral | Wait until oscillation disapears | - | - | - | Do not exceed 111 kt | - | Several dutch roll oscillations
103 | 103 | 8 | Dutch roll manoeuvre | 1 |  | 3 | Aft | High | 3500 ft | Up | Low | 70 | Medium | fly level | LEFT-RIGHT |  | Set configuration, A/C must keep attitude for 20s | Doublet input until ball about 1 off | Set pedals back to neutral | Wait until oscillation disapears | - | - | - | Do not exceed 111 kt | - | Several dutch roll oscillations
104 | 104 | 8 | Dutch roll manoeuvre | 1 |  | 3 | Aft | High | 3500 ft | Up | Low | 70 | Medium | fly level | LEFT-RIGHT |  | Set configuration, A/C must keep attitude for 20s | Doublet input until ball about 1 off | Set pedals back to neutral | Wait until oscillation disapears | - | - | - | Do not exceed 111 kt | - | Several dutch roll oscillations
105 | 105 | 10 | Dutch roll manoeuvre | 0 |  | 3 | Aft | High | 3500 ft | Up | Medium | 80 | Medium | fly level | LEFT-RIGHT |  | Set configuration, A/C must keep attitude for 20s | Doublet input until ball about 1 off | Set pedals back to neutral | Wait until oscillation disapears | - | - | - | Do not exceed 111 kt | - | Several dutch roll oscillations
106 | 106 | 10 | Dutch roll manoeuvre | 0 |  | 3 | Aft | High | 3500 ft | Up | Medium | 80 | Medium | fly level | LEFT-RIGHT |  | Set configuration, A/C must keep attitude for 20s | Doublet input until ball about 1 off | Set pedals back to neutral | Wait until oscillation disapears | - | - | - | Do not exceed 111 kt | - | Several dutch roll oscillations
107 | 107 | 16 | Dutch roll manoeuvre | 1 |  | 3 | Fwd | Medium | 6500 ft | Up | Medium | 80 | High | climb | RIGHT-LEFT |  | Set configuration, A/C must keep attitude for 20s | Doublet input until ball about 1 off | Set pedals back to neutral | Wait until oscillation disapears | - | - | - | Do not exceed 111 kt | - | Several dutch roll oscillations
108 | 108 | 16 | Dutch roll manoeuvre | 1 |  | 3 | Fwd | Medium | 6500 ft | Up | Medium | 80 | High | climb | LEFT-RIGHT |  | Set configuration, A/C must keep attitude for 20s | Doublet input until ball about 1 off | Set pedals back to neutral | Wait until oscillation disapears | - | - | - | Do not exceed 111 kt | - | Several dutch roll oscillations
109 | 109 | 1 | Steady heading steady sideslip #1 | 1 |  | 5 | Fwd | Medium | 6500 ft | Up | Low | 70 | Medium | fly level | LEFT |  | Set configuration, A/C must keep attitude for 20s | Gradual pedal input to LEFT | Maintain sideslip and heading for 10-15s using ailerons | Pedal to neutral and wait for 10s | Gradual pedal input to RIGHT | Maintain sideslip and heading for 10-15s using ailerons | Pedal to neutral and wait for 10s | Do not exceed 111 kt | Maintain track angle by adjust bank by applying aileron, no dutch roll motion! | Undisturbed
110 | 110 | 3 | Steady heading steady sideslip #1 | 1 |  | 5 | Fwd | Medium | 6500 ft | Up | Low | 70 | Medium | fly level | LEFT |  | Set configuration, A/C must keep attitude for 20s | Gradual pedal input to LEFT | Maintain sideslip and heading for 10-15s using ailerons | Pedal to neutral and wait for 10s | Gradual pedal input to RIGHT | Maintain sideslip and heading for 10-15s using ailerons | Pedal to neutral and wait for 10s | Do not exceed 111 kt | Maintain track angle by adjust bank by applying aileron, no dutch roll motion! | Undisturbed
111 | 111 | 15 | Steady heading steady sideslip #1 | 1 | 1 | 5 | Fwd | Medium | 6500 ft | Up | Medium | 80 | Medium | fly level | LEFT |  | Set configuration, A/C must keep attitude for 20s | Gradual pedal input to LEFT | Maintain sideslip and heading for 10-15s using ailerons | Pedal to neutral and wait for 10s | Gradual pedal input to RIGHT | Maintain sideslip and heading for 10-15s using ailerons | Pedal to neutral and wait for 10s | Do not exceed 111 kt | Maintain track angle by adjust bank by applying aileron, no dutch roll motion! | Undisturbed
112 | 112 | 7 | Steady heading steady sideslip #1 | 1 |  | 5 | Fwd | Medium | 6500 ft | Up | Medium | 80 | Medium | fly level | LEFT |  | Set configuration, A/C must keep attitude for 20s | Gradual pedal input to LEFT | Maintain sideslip and heading for 10-15s using ailerons | Pedal to neutral and wait for 10s | Gradual pedal input to RIGHT | Maintain sideslip and heading for 10-15s using ailerons | Pedal to neutral and wait for 10s | Do not exceed 111 kt | Maintain track angle by adjust bank by applying aileron, no dutch roll motion! | Undisturbed
113 | 113 | 9 | Steady heading steady sideslip #1 | 1 |  | 5 | Fwd | Medium | 6500 ft | Up | Low | 70 | Medium | fly level | RIGHT |  | Set configuration, A/C must keep attitude for 20s | Gradual pedal input to RIGHT | Maintain sideslip and heading for 10-15s using ailerons | Pedal to neutral and wait for 10s | Gradual pedal input to LEFT | Maintain sideslip and heading for 10-15s using ailerons | Pedal to neutral and wait for 10s | Do not exceed 111 kt | Maintain track angle by adjust bank by applying aileron, no dutch roll motion! | Undisturbed
114 | 114 | 11 | Steady heading steady sideslip #1 | 1 | 1 | 5 | Fwd | Medium | 6500 ft | Up | Low | 70 | Medium | fly level | RIGHT |  | Set configuration, A/C must keep attitude for 20s | Gradual pedal input to RIGHT | Maintain sideslip and heading for 10-15s using ailerons | Pedal to neutral and wait for 10s | Gradual pedal input to LEFT | Maintain sideslip and heading for 10-15s using ailerons | Pedal to neutral and wait for 10s | Do not exceed 111 kt | Maintain track angle by adjust bank by applying aileron, no dutch roll motion! | Undisturbed
1151 | 115 | 13 | Steady heading steady sideslip #1 | 1 | 1 | 5 | Fwd | Medium | 6500 ft | Up | Medium | 80 | Medium | fly level | RIGHT |  | Set configuration, A/C must keep attitude for 20s | Gradual pedal input to RIGHT | Maintain sideslip and heading for 10-15s using ailerons | Pedal to neutral and wait for 10s | Gradual pedal input to LEFT | Maintain sideslip and heading for 10-15s using ailerons | Pedal to neutral and wait for 10s | Do not exceed 111 kt | Maintain track angle by adjust bank by applying aileron, no dutch roll motion! | Undisturbed
1152 | 115 | 13 | Steady heading steady sideslip #1 | 1 | 1 | 5 | Fwd | Medium | 6500 ft | Up | Medium | 80 | Medium | fly level | RIGHT |  | Set configuration, A/C must keep attitude for 20s | Gradual pedal input to RIGHT | Maintain sideslip and heading for 10-15s using ailerons | Pedal to neutral and wait for 10s | Gradual pedal input to LEFT | Maintain sideslip and heading for 10-15s using ailerons | Pedal to neutral and wait for 10s | Do not exceed 111 kt | Maintain track angle by adjust bank by applying aileron, no dutch roll motion! | Undisturbed
1161 | 116 | 13 | Steady heading steady sideslip #1 | 1 | 0.9 | 5 | Fwd | Medium | 6500 ft | Up | Medium | 80 | Medium | fly level | RIGHT |  | Set configuration, A/C must keep attitude for 20s | Gradual pedal input to RIGHT | Maintain sideslip and heading for 10-15s using ailerons | Pedal to neutral and wait for 10s | Gradual pedal input to LEFT | Maintain sideslip and heading for 10-15s using ailerons | Pedal to neutral and wait for 10s | Do not exceed 111 kt | Maintain track angle by adjust bank by applying aileron, no dutch roll motion! | Undisturbed
1162 | 116 | 13 | Steady heading steady sideslip #1 | 1 | 0.9 | 5 | Fwd | Medium | 6500 ft | Up | Medium | 80 | Medium | fly level | RIGHT |  | Set configuration, A/C must keep attitude for 20s | Gradual pedal input to RIGHT | Maintain sideslip and heading for 10-15s using ailerons | Pedal to neutral and wait for 10s | Gradual pedal input to LEFT | Maintain sideslip and heading for 10-15s using ailerons | Pedal to neutral and wait for 10s | Do not exceed 111 kt | Maintain track angle by adjust bank by applying aileron, no dutch roll motion! | Undisturbed
117 | 117 | 3 | Steady heading steady sideslip #2 | 1 |  | 5 | Fwd | Medium | 6500 ft | Up | Medium | 80 | Low | descent | LEFT |  | Set configuration, A/C must keep attitude for 20s | Gradual pedal input to LEFT | Maintain sideslip and heading for 10-15s using ailerons | Pedal to neutral and wait for 10s | Gradual pedal input to RIGHT | Maintain sideslip and heading for 10-15s using ailerons | Pedal to neutral and wait for 10s | Do not exceed 111 kt | Maintain track angle by adjust bank by applying aileron, no dutch roll motion! | Undisturbed
118 | 118 | 7 | Steady heading steady sideslip #2 | 1 |  | 5 | Fwd | Medium | 6500 ft | Up | Medium | 80 | Low | descent | LEFT |  | Set configuration, A/C must keep attitude for 20s | Gradual pedal input to LEFT | Maintain sideslip and heading for 10-15s using ailerons | Pedal to neutral and wait for 10s | Gradual pedal input to RIGHT | Maintain sideslip and heading for 10-15s using ailerons | Pedal to neutral and wait for 10s | Do not exceed 111 kt | Maintain track angle by adjust bank by applying aileron, no dutch roll motion! | Undisturbed
119 | 119 | 9 | Steady heading steady sideslip #2 | 1 |  | 5 | Fwd | Medium | 6500 ft | Up | Medium | 80 | Max | descent | LEFT |  | Set configuration, A/C must keep attitude for 20s | Gradual pedal input to LEFT | Maintain sideslip and heading for 10-15s using ailerons | Pedal to neutral and wait for 10s | Gradual pedal input to RIGHT | Maintain sideslip and heading for 10-15s using ailerons | Pedal to neutral and wait for 10s | Do not exceed 111 kt | Maintain track angle by adjust bank by applying aileron, no dutch roll motion! | Undisturbed
120 | 120 | 15 | Steady heading steady sideslip #2 | 1 | 1 | 5 | Fwd | Medium | 6500 ft | Up | Medium | 80 | Max | climb | LEFT |  | Set configuration, A/C must keep attitude for 20s | Gradual pedal input to LEFT | Maintain sideslip and heading for 10-15s using ailerons | Pedal to neutral and wait for 10s | Gradual pedal input to RIGHT | Maintain sideslip and heading for 10-15s using ailerons | Pedal to neutral and wait for 10s | Do not exceed 111 kt | Maintain track angle by adjust bank by applying aileron, no dutch roll motion! | Undisturbed
121 | 121 | 1 | T/O | 1 |  | 7 | Fwd | - | #N/A | UP | - | #N/A | - | #N/A | - |  | Set flaps to UP | Perform T/O according to AFM | - | - | - | - | - | Do not exceed 111 kt | - | -
122 | 122 | 3 | T/O | 1 |  | 7 | Fwd | - | #N/A | UP | - | #N/A | - | #N/A | - |  | Set flaps to UP | Perform T/O according to AFM | - | - | - | - | - | Do not exceed 111 kt | - | -
123 | 123 | 5 | T/O | 1 |  | 7 | Fwd | - | #N/A | 25° | - | #N/A | - | #N/A | - |  | Set flaps to 25° | Perform T/O according to AFM | - | - | - | - | - | Do not exceed 111 kt | - | -
124 | 124 | 9 | T/O | 1 |  | 7 | Fwd | - | #N/A | 25° | - | #N/A | - | #N/A | - |  | Set flaps to 25° | Perform T/O according to AFM | - | - | - | - | - | Do not exceed 111 kt | - | -
125 | 125 | 11 | T/O | 1 |  | 7 | Fwd | - | #N/A | 40° | - | #N/A | - | #N/A | - |  | Set flaps to 40° | Perform T/O according to AFM | - | - | - | - | - | Do not exceed 111 kt | - | -
126 | 126 | 14 | T/O | 1 |  | 7 | Fwd | - | #N/A | 40° | - | #N/A | - | #N/A | - |  | Set flaps to 40° | Perform T/O according to AFM | - | - | - | - | - | Do not exceed 111 kt | - | -
127 | 127 | 2 | T/O | 1 |  | 7 | Aft | - | #N/A | UP | - | #N/A | - | #N/A | - |  | Set flaps to UP | Perform T/O according to AFM | - | - | - | - | - | Do not exceed 111 kt | - | -
128 | 128 | 4 | T/O | 1 |  | 7 | Aft | - | #N/A | UP | - | #N/A | - | #N/A | - |  | Set flaps to UP | Perform T/O according to AFM | - | - | - | - | - | Do not exceed 111 kt | - | -
129 | 129 | 6 | T/O | 1 |  | 7 | Aft | - | #N/A | 25° | - | #N/A | - | #N/A | - |  | Set flaps to 25° | Perform T/O according to AFM | - | - | - | - | - | Do not exceed 111 kt | - | -
130 | 130 | 8 | T/O | 1 |  | 7 | Aft | - | #N/A | 25° | - | #N/A | - | #N/A | - |  | Set flaps to 25° | Perform T/O according to AFM | - | - | - | - | - | Do not exceed 111 kt | - | -
131 | 131 | 10 | T/O | 1 |  | 7 | Aft | - | #N/A | 40° | - | #N/A | - | #N/A | - |  | Set flaps to 40° | Perform T/O according to AFM | - | - | - | - | - | Do not exceed 111 kt | - | -
132 | 132 | 12 | T/O | 1 |  | 7 | Aft | - | #N/A | 40° | - | #N/A | - | #N/A | - |  | Set flaps to 40° | Perform T/O according to AFM | - | - | - | - | - | Do not exceed 111 kt | - | -
133 | 133 | 1 | Landing | 1 |  | 7 | Fwd | - | #N/A | UP | - | #N/A | - | #N/A | - |  | Set flaps to UP | Perform Landing according to AFM | - | - | - | - | - | Do not exceed 111 kt | - | -
134 | 134 | 3 | Landing | 1 |  | 7 | Fwd | - | #N/A | UP | - | #N/A | - | #N/A | - |  | Set flaps to UP | Perform Landing according to AFM | - | - | - | - | - | Do not exceed 111 kt | - | -
135 | 135 | 5 | Landing | 0 |  | 7 | Fwd | - | #N/A | 25° | - | #N/A | - | #N/A | - |  | Set flaps to 25° | Perform Landing according to AFM | - | - | - | - | - | Do not exceed 111 kt | - | -
136 | 136 | 7 | Landing | 0 |  | 7 | Fwd | - | #N/A | 25° | - | #N/A | - | #N/A | - |  | Set flaps to 25° | Perform Landing according to AFM | - | - | - | - | - | Do not exceed 111 kt | - | -
137 | 137 | 9 | Landing | 1 |  | 7 | Fwd | - | #N/A | 40° | - | #N/A | - | #N/A | - |  | Set flaps to 40° | Perform Landing according to AFM | - | - | - | - | - | Do not exceed 111 kt | - | -
138 | 138 | 11 | Landing | 1 |  | 7 | Fwd | - | #N/A | 40° | - | #N/A | - | #N/A | - |  | Set flaps to 40° | Perform Landing according to AFM | - | - | - | - | - | Do not exceed 111 kt | - | -
139 | 139 | 2 | Landing | 0 |  | 7 | Aft | - | #N/A | UP | - | #N/A | - | #N/A | - |  | Set flaps to UP | Perform Landing according to AFM | - | - | - | - | - | Do not exceed 111 kt | - | -
140 | 140 | 4 | Landing | 0 |  | 7 | Aft | - | #N/A | UP | - | #N/A | - | #N/A | - |  | Set flaps to UP | Perform Landing according to AFM | - | - | - | - | - | Do not exceed 111 kt | - | -
141 | 141 | 16 | Landing | 1 |  | 7 | Fwd | - | #N/A | 25° | - | #N/A | - | #N/A | - |  | Set flaps to 25° | Perform Landing according to AFM | - | - | - | - | - | Do not exceed 111 kt | - | -
142 | 142 | 8 | Landing | 1 |  | 7 | Aft | - | #N/A | 25° | - | #N/A | - | #N/A | - |  | Set flaps to 25° | Perform Landing according to AFM | - | - | - | - | - | Do not exceed 111 kt | - | -
143 | 143 | 17 | Landing | 0 |  | 7 | Aft | - | #N/A | 40° | - | #N/A | - | #N/A | - |  | Set flaps to 40° | Perform Landing according to AFM | - | - | - | - | - | Do not exceed 111 kt | - | -
144 | 144 | 12 | Landing | 0 |  | 7 | Aft | - | #N/A | 40° | - | #N/A | - | #N/A | - |  | Set flaps to 40° | Perform Landing according to AFM | - | - | - | - | - | Do not exceed 111 kt | - | -
145 | 145 | 14 | Go around | 0 |  | 7 | Fwd | - | #N/A | 25° | - | #N/A | - | #N/A | - |  | Set flaps to 25° | Perform Go around according to AFM | - | - | - | - | - | Do not exceed 111 kt | - | -
146 | 146 | 14 | Go around | 0 |  | 7 | Fwd | - | #N/A | 25° | - | #N/A | - | #N/A | - |  | Set flaps to 25° | Perform Go around according to AFM | - | - | - | - | - | Do not exceed 111 kt | - | -
147 | 147 | 3 | Spiral-Check | 1 |  | 4 | Fwd | Medium | 6500 ft | UP | Medium | 80 | Medium | fly level | LEFT |  | Set configuration, A/C must keep attitude for 20s | Roll LEFT to 30° bank and stabilize | Remove hands and feet from inputs | Terminate manoeuvre if bank angle outside 10° to 45° | - | - | - | Do not exceed 111 kt | Abort test if it lasts longer than 60s | Manoeuvre lasts for at least 20s
148 | 148 | 3 | Spiral-Check | 1 |  | 4 | Fwd | Medium | 6500 ft | UP | Medium | 80 | Medium | fly level | LEFT |  | Set configuration, A/C must keep attitude for 20s | Roll LEFT to 30° bank and stabilize | Remove hands and feet from inputs | Terminate manoeuvre if bank angle outside 10° to 45° | - | - | - | Do not exceed 111 kt | Abort test if it lasts longer than 60s | Manoeuvre lasts for at least 20s
149 | 149 | 5 | Spiral-Check | 1 |  | 4 | Fwd | Medium | 6500 ft | UP | Medium | 80 | Medium | fly level | RIGHT |  | Set configuration, A/C must keep attitude for 20s | Roll RIGHT to 30° bank and stabilize | Remove hands and feet from inputs | Terminate manoeuvre if bank angle outside 10° to 45° | - | - | - | Do not exceed 111 kt | Abort test if it lasts longer than 60s | Manoeuvre lasts for at least 20s
150 | 150 | 7 | Spiral-Check | 1 |  | 4 | Fwd | Medium | 6500 ft | UP | Medium | 80 | Medium | fly level | RIGHT |  | Set configuration, A/C must keep attitude for 20s | Roll RIGHT to 30° bank and stabilize | Remove hands and feet from inputs | Terminate manoeuvre if bank angle outside 10° to 45° | - | - | - | Do not exceed 111 kt | Abort test if it lasts longer than 60s | Manoeuvre lasts for at least 20s
151 | 151 | 11 | Spiral-Check | 1 |  | 4 | Fwd | High | 3500 ft | UP | Medium | 80 | Medium | fly level | LEFT |  | Set configuration, A/C must keep attitude for 20s | Roll LEFT to 30° bank and stabilize | Remove hands and feet from inputs | Terminate manoeuvre if bank angle outside 10° to 45° | - | - | - | Do not exceed 111 kt | Abort test if it lasts longer than 60s | Manoeuvre lasts for at least 20s
152 | 152 | 13 | Spiral-Check | 1 |  | 4 | Fwd | High | 3500 ft | UP | Medium | 80 | Medium | fly level | LEFT |  | Set configuration, A/C must keep attitude for 20s | Roll LEFT to 30° bank and stabilize | Remove hands and feet from inputs | Terminate manoeuvre if bank angle outside 10° to 45° | - | - | - | Do not exceed 111 kt | Abort test if it lasts longer than 60s | Manoeuvre lasts for at least 20s
153 | 153 | 13 | Spiral-Check | 1 |  | 4 | Fwd | High | 3500 ft | UP | Medium | 80 | Medium | fly level | RIGHT |  | Set configuration, A/C must keep attitude for 20s | Roll RIGHT to 30° bank and stabilize | Remove hands and feet from inputs | Terminate manoeuvre if bank angle outside 10° to 45° | - | - | - | Do not exceed 111 kt | Abort test if it lasts longer than 60s | Manoeuvre lasts for at least 20s
154 | 154 | 17 | Spiral-Check | 1 |  | 4 | Fwd | High | 3500 ft | UP | Medium | 80 | Medium | fly level | RIGHT |  | Set configuration, A/C must keep attitude for 20s | Roll RIGHT to 30° bank and stabilize | Remove hands and feet from inputs | Terminate manoeuvre if bank angle outside 10° to 45° | - | - | - | Do not exceed 111 kt | Abort test if it lasts longer than 60s | Manoeuvre lasts for at least 20s
155 | 155 | 17 | Spiral-Check | 1 |  | 4 | Aft | Medium | 6500 ft | UP | Medium | 80 | Medium | fly level | LEFT |  | Set configuration, A/C must keep attitude for 20s | Roll LEFT to 30° bank and stabilize | Remove hands and feet from inputs | Terminate manoeuvre if bank angle outside 10° to 45° | - | - | - | Do not exceed 111 kt | Abort test if it lasts longer than 60s | Manoeuvre lasts for at least 20s
156 | 156 | 4 | Spiral-Check | 0 |  | 4 | Aft | Medium | 6500 ft | UP | Medium | 80 | Medium | fly level | LEFT |  | Set configuration, A/C must keep attitude for 20s | Roll LEFT to 30° bank and stabilize | Remove hands and feet from inputs | Terminate manoeuvre if bank angle outside 10° to 45° | - | - | - | Do not exceed 111 kt | Abort test if it lasts longer than 60s | Manoeuvre lasts for at least 20s
157 | 157 | 6 | Spiral-Check | 1 |  | 4 | Aft | Medium | 6500 ft | UP | Medium | 80 | Medium | fly level | RIGHT |  | Set configuration, A/C must keep attitude for 20s | Roll RIGHT to 30° bank and stabilize | Remove hands and feet from inputs | Terminate manoeuvre if bank angle outside 10° to 45° | - | - | - | Do not exceed 111 kt | Abort test if it lasts longer than 60s | Manoeuvre lasts for at least 20s
158 | 158 | 8 | Spiral-Check | 1 |  | 4 | Aft | Medium | 6500 ft | UP | Medium | 80 | Medium | fly level | RIGHT |  | Set configuration, A/C must keep attitude for 20s | Roll RIGHT to 30° bank and stabilize | Remove hands and feet from inputs | Terminate manoeuvre if bank angle outside 10° to 45° | - | - | - | Do not exceed 111 kt | Abort test if it lasts longer than 60s | Manoeuvre lasts for at least 20s
159 | 159 | 8 | Spiral-Check | 1 |  | 4 | Aft | High | 3500 ft | UP | Medium | 80 | Medium | fly level | LEFT |  | Set configuration, A/C must keep attitude for 20s | Roll LEFT to 30° bank and stabilize | Remove hands and feet from inputs | Terminate manoeuvre if bank angle outside 10° to 45° | - | - | - | Do not exceed 111 kt | Abort test if it lasts longer than 60s | Manoeuvre lasts for at least 20s
160 | 160 | 17 | Spiral-Check | 1 |  | 4 | Aft | High | 3500 ft | UP | Medium | 80 | Medium | fly level | LEFT |  | Set configuration, A/C must keep attitude for 20s | Roll LEFT to 30° bank and stabilize | Remove hands and feet from inputs | Terminate manoeuvre if bank angle outside 10° to 45° | - | - | - | Do not exceed 111 kt | Abort test if it lasts longer than 60s | Manoeuvre lasts for at least 20s
161 | 161 | 17 | Spiral-Check | 1 |  | 4 | Aft | High | 3500 ft | UP | Medium | 80 | Medium | fly level | RIGHT |  | Set configuration, A/C must keep attitude for 20s | Roll RIGHT to 30° bank and stabilize | Remove hands and feet from inputs | Terminate manoeuvre if bank angle outside 10° to 45° | - | - | - | Do not exceed 111 kt | Abort test if it lasts longer than 60s | Manoeuvre lasts for at least 20s
162 | 162 | 12 | Spiral-Check | 0 |  | 4 | Aft | High | 3500 ft | UP | Medium | 80 | Medium | fly level | RIGHT |  | Set configuration, A/C must keep attitude for 20s | Roll RIGHT to 30° bank and stabilize | Remove hands and feet from inputs | Terminate manoeuvre if bank angle outside 10° to 45° | - | - | - | Do not exceed 111 kt | Abort test if it lasts longer than 60s | Manoeuvre lasts for at least 20s
163 | 163 | 5 | Stall | 1 | 0.5 | 5 | Fwd | Medium | 6500 ft | UP | Medium | 80 | Medium | fly level | - |  | Set configuration, A/C must keep attitude for 20s | Decrease power | Speed should decrease with 1kn/s | Hold altitude with elevator | Wait until attitude negative, accelerate back to initial condition | - | - | Do not exceed 111 kt | - | Wings level during whole manoeuvre
164 | 164 | 9 | Stall | 1 |  | 5 | Fwd | Medium | 6500 ft | UP | Medium | 80 | Medium | fly level | - |  | Set configuration, A/C must keep attitude for 20s | Decrease power | Speed should decrease with 1kn/s | Hold altitude with elevator | Wait until attitude negative, accelerate back to initial condition | - | - | Do not exceed 111 kt | - | Wings level during whole manoeuvre
162 | 162 | 15 | Stall | 1 | 1 | 5 | Fwd | Medium | 6500 ft | UP | Medium | 80 | Medium | fly level | - |  | Set configuration, A/C must keep attitude for 20s | Decrease power | Speed should decrease with 1kn/s | Hold altitude with elevator | Wait until attitude negative, accelerate back to initial condition | - | - | Do not exceed 111 kt | - | Wings level during whole manoeuvre
166 | 166 | 12 | Stall | 1 |  | 5 | Aft | Medium | 6500 ft | UP | Medium | 80 | Medium | fly level | - |  | Set configuration, A/C must keep attitude for 20s | Decrease power | Speed should decrease with 1kn/s | Hold altitude with elevator | Wait until attitude negative, accelerate back to initial condition | - | - | Do not exceed 111 kt | - | Wings level during whole manoeuvre
167 | 167 | 0 | Short period #1 | 1 |  | 3 | Aft | Medium | 6500 ft | Up | Medium | 80 | Medium | fly level | PUSH-PULL | free / fixed | Set configuration, A/C must keep attitude for 20s | Short PUSH-PULL-pulse on elevator, AOA change ~±3° | Bring yoke back to trim position | Wait until oscillation disapears | - | - | - | Do not exceed 111 kt | Avoid maintaining angle of attack, Get a feeling for the input to excite A/C the best | Several oscillations on lateral axis
168 | 168 | 0 | Phugoid | 1 |  | 5 | Aft | Medium | 6500 ft | Up | Medium | 80 | Medium | fly level | PULL | free | Set configuration, A/C must keep attitude for 20s | PULL Elevator until IAS 68 | Wait at least for 2 periods, then abort to level flight | - | - | - | - | Do not exceed 111 kt | If possible, three full cycles, Check whether initial speed is to high or to low in order not to exceed VNE or undershoot VS | Several oscillations on lateral axis
169 | 169 | 0 | Pushover-pull-up | 1 |  | 5 | Aft | Medium | 6500 ft | Up | Medium | 80 | Medium | fly level | PUSH | free / fixed | Set configuration, A/C must keep attitude for 20s | Slowly and continuously push stick until IAS 92 | Slowly and continuously pull stick until above IAS 48 | Push stick slowly and return to trim condition | - | - | - | Do not exceed 111 kt | Constant power, Check whether initial speed is to high or to low in order not to exceed VNE or undershoot VS | Smooth/continuous change in IAS
170 | 170 | 0 | Level turn | 1 |  | 3 | Aft | Medium | 6500 ft | Up | Medium | 80 | Medium | fly level | RIGHT | free / fixed | Set configuration, A/C must keep attitude for 20s | Bank RIGHT (10 deg/s) until 45 deg reached | Keep angle for 15s | Bank LEFT (10 deg/s) until 45 deg reached | Keep angle for 15s | Return to wings-level trim condition | - | Do not exceed 111 kt | Hold altitude with additional power, Check whether 10 °=s is to fast for a smooth turn | Undisturbed
171 | 171 | 0 | Thrust variation | 1 |  | 4 | Aft | Medium | 6500 ft | Up | Medium | 80 | Medium | fly level | Single | free / fixed | Set configuration, A/C must keep attitude for 20s | Remove hands from yoke and feet from pedals | Push power rapidly to maxiumum | Wait until A/C stabilized again | Pull power lever rapidly to idle | Wait until A/C stabilized again | Return to trim condition | Do not exceed 111 kt | Engine must not over-rev, Find out the optimal maximum power lever setting which will not over-rev the engine | Undisturbed
172 | 172 | 0 | Bank-to-bank roll | 1 |  | 3 | Aft | Medium | 6500 ft | Up | Medium | 80 | Medium | fly level | RIGHT | free / fixed | Set configuration, A/C must keep attitude for 20s | Sharp input to bank RIGHT until 30 deg reached | Keep angle for 10s | #REF! | Keep angle for 10 seconds | Return to wings-level trim condition | - | Do not exceed 111 kt | Check for practicability | Undisturbed
173 | 173 | 0 | Dutch roll manoeuvre | 1 |  | 3 | Aft | Medium | 6500 ft | Up | Medium | 80 | Medium | fly level | LEFT-RIGHT |  | Set configuration, A/C must keep attitude for 20s | Doublet input until ball about 1 off | Set pedals back to neutral | Wait until oscillation disapears | - | - | - | Do not exceed 111 kt | Check for practicability | Several dutch roll oscillations
174 | 174 | 0 | Steady heading steady sideslip #1 | 1 |  | 5 | Aft | Medium | 6500 ft | Up | Medium | 80 | Medium | fly level | RIGHT |  | Set configuration, A/C must keep attitude for 20s | Gradual pedal input to RIGHT | Maintain sideslip and heading for 10-15s using ailerons | Pedal to neutral and wait for 10s | Gradual pedal input to LEFT | Maintain sideslip and heading for 10-15s using ailerons | Pedal to neutral and wait for 10s | Do not exceed 111 kt | Maintain track angle by adjust bank by applying aileron, no dutch roll motion!, Check for practicability | Undisturbed
175 | 175 | 0 | Spiral-Check | 1 |  | 4 | Aft | Medium | 6500 ft | UP | Medium | 80 | Medium | fly level | RIGHT |  | Set configuration, A/C must keep attitude for 20s | Roll RIGHT to 30° bank and stabilize | Remove hands and feet from inputs | Terminate manoeuvre if bank angle outside 10° to 45° | - | - | - | Do not exceed 111 kt | Abort test if it lasts longer than 60s, Check for practicability | Manoeuvre lasts for at least 20s
176 | 176 | 0 | Stall | 1 |  | 5 | Aft | Medium | 6500 ft | UP | Medium | 80 | Medium | fly level | - |  | Set configuration, A/C must keep attitude for 20s | Decrease power | Speed should decrease with 1kn/s | Hold altitude with elevator | Wait until attitude negative, accelerate back to initial condition | - | - | Do not exceed 111 kt | Check for practicability | Wings level during whole manoeuvre
177 | 177 | 15 | Stall | 1 | 1 | 5 | Fwd | Medium | 6500 ft | UP | Medium |  | Medium | 2400rpm | - |  | Set configuration, A/C must keep attitude for 20s | Decrease power | Speed should decrease with 1kn/s | Hold altitude with elevator | Wait until attitude negative, accelerate back to initial condition | - | - | Do not exceed 111 kt | - | Wings level during whole manoeuvre
178 | 178 | 15 | Stall | 1 | 1 | 5 | Fwd | Medium | 6500 ft | UP | Medium |  | Medium | 2400rpm | - |  | Set configuration, A/C must keep attitude for 20s | Decrease power | Speed should decrease with 1kn/s | Hold altitude with elevator | Wait until attitude negative, accelerate back to initial condition | - | - | Do not exceed 111 kt | - | Wings level during whole manoeuvre
179 | 179 | 15 | Stall | 1 | 1 | 5 | Fwd | Medium | 6500 ft | UP | Medium |  | Medium | 2400rpm | - |  | Set configuration, A/C must keep attitude for 20s | Decrease power | Speed should decrease with 1kn/s | Hold altitude with elevator | Wait until attitude negative, accelerate back to initial condition | - | - | Do not exceed 111 kt | - | Wings level during whole manoeuvre
180 | 180 | 15 | Steady heading steady sideslip #1 | 1 | 1 | 5 | Fwd | Medium | 6500 ft | Up | Medium | 80 | Low | descent | RIGHT |  | Set configuration, A/C must keep attitude for 20s | Gradual pedal input to LEFT | Maintain sideslip and heading for 10-15s using ailerons | Pedal to neutral and wait for 10s | Gradual pedal input to RIGHT | Maintain sideslip and heading for 10-15s using ailerons | Pedal to neutral and wait for 10s | Do not exceed 111 kt | Maintain track angle by adjust bank by applying aileron, no dutch roll motion! | Undisturbed
181 | 181 | 15 | Steady heading steady sideslip #2 | 1 | 1 | 5 | Fwd | Medium | 6500 ft | Up | Medium | 80 | Max | climb | RIGHT |  | Set configuration, A/C must keep attitude for 20s | Gradual pedal input to LEFT | Maintain sideslip and heading for 10-15s using ailerons | Pedal to neutral and wait for 10s | Gradual pedal input to RIGHT | Maintain sideslip and heading for 10-15s using ailerons | Pedal to neutral and wait for 10s | Do not exceed 111 kt | Maintain track angle by adjust bank by applying aileron, no dutch roll motion! | Undisturbed
182 | 182 | 16 | T/O | 1 |  | 7 | Fwd | - | #N/A | 25° | - | #N/A | - | #N/A | - |  | Set flaps to 25° | Perform T/O according to AFM | - | - | - | - | - | Do not exceed 111 kt | - | -
183 | 183 | 16 | Bank-to-bank roll | 1 |  | 3 | Fwd | Medium | 6500 ft | Up | Medium | 80 | Low | descent | RIGHT | free / fixed | Set configuration, A/C must keep attitude for 20s | Sharp input to bank RIGHT until 30 deg reached | Keep angle for 10s | Sharp input to bank LEFT until 30 deg reached | Keep angle for 10 seconds | Return to wings-level trim condition | - | Do not exceed 111 kt | - | Undisturbed
184 | 184 | 16 | Bank-to-bank roll | 1 |  | 3 | Fwd | Medium | 6500 ft | Up | Medium | 80 | Low | descent | RIGHT | free / fixed | Set configuration, A/C must keep attitude for 20s | Sharp input to bank RIGHT until 30 deg reached | Keep angle for 10s | Sharp input to bank LEFT until 30 deg reached | Keep angle for 10 seconds | Return to wings-level trim condition | - | Do not exceed 111 kt | - | Undisturbed
185 | 185 | 16 | Bank-to-bank roll | 1 |  | 3 | Fwd | Medium | 6500 ft | Up | Medium | 80 | High | climb | RIGHT | free / fixed | Set configuration, A/C must keep attitude for 20s | Sharp input to bank RIGHT until 30 deg reached | Keep angle for 10s | Sharp input to bank LEFT until 30 deg reached | Keep angle for 10 seconds | Return to wings-level trim condition | - | Do not exceed 111 kt | - | Undisturbed
186 | 186 | 16 | Bank-to-bank roll | 1 |  | 3 | Fwd | Medium | 6500 ft | Up | Medium | 80 | High | climb | RIGHT | free / fixed | Set configuration, A/C must keep attitude for 20s | Sharp input to bank RIGHT until 30 deg reached | Keep angle for 10s | Sharp input to bank LEFT until 30 deg reached | Keep angle for 10 seconds | Return to wings-level trim condition | - | Do not exceed 111 kt | - | Undisturbed
187 | 187 | 16 | Steady heading steady sideslip #2 | 1 | 0.5 | 5 | Fwd | Medium | 6500 ft | Up | Medium | 80 | Low | descent | RIGHT |  | Set configuration, A/C must keep attitude for 20s | Gradual pedal input to LEFT | Maintain sideslip and heading for 10-15s using ailerons | Pedal to neutral and wait for 10s | Gradual pedal input to RIGHT | Maintain sideslip and heading for 10-15s using ailerons | Pedal to neutral and wait for 10s | Do not exceed 111 kt | Maintain track angle by adjust bank by applying aileron, no dutch roll motion! | Undisturbed
188 | 188 | 16 | Steady heading steady sideslip #2 | 1 | 0.8 | 5 | Fwd | Medium | 6500 ft | Up | Medium | 80 | Low | descent | LEFT |  | Set configuration, A/C must keep attitude for 20s | Gradual pedal input to LEFT | Maintain sideslip and heading for 10-15s using ailerons | Pedal to neutral and wait for 10s | Gradual pedal input to RIGHT | Maintain sideslip and heading for 10-15s using ailerons | Pedal to neutral and wait for 10s | Do not exceed 111 kt | Maintain track angle by adjust bank by applying aileron, no dutch roll motion! | Undisturbed
189 | 189 | 16 | Steady heading steady sideslip #2 | 1 | 1 | 5 | Fwd | Medium | 6500 ft | Up | Medium | 80 | High | climb | RIGHT |  | Set configuration, A/C must keep attitude for 20s | Gradual pedal input to LEFT | Maintain sideslip and heading for 10-15s using ailerons | Pedal to neutral and wait for 10s | Gradual pedal input to RIGHT | Maintain sideslip and heading for 10-15s using ailerons | Pedal to neutral and wait for 10s | Do not exceed 111 kt | Maintain track angle by adjust bank by applying aileron, no dutch roll motion! | Undisturbed
190 | 190 | 16 | Steady heading steady sideslip #2 | 1 | 1 | 5 | Fwd | Medium | 6500 ft | Up | Medium | 80 | High | climb | LEFT |  | Set configuration, A/C must keep attitude for 20s | Gradual pedal input to LEFT | Maintain sideslip and heading for 10-15s using ailerons | Pedal to neutral and wait for 10s | Gradual pedal input to RIGHT | Maintain sideslip and heading for 10-15s using ailerons | Pedal to neutral and wait for 10s | Do not exceed 111 kt | Maintain track angle by adjust bank by applying aileron, no dutch roll motion! | Undisturbed
1001 | 1001 | 6 | Climb | 1 |  |  | Aft | Medium | 6500 ft | Up | Low | 70 | High | climb
1002 | 1002 | 6 | Climb | 1 |  |  | Aft | Medium | 6500 ft | Up | Medium | 80 | High | climb
1003 | 1003 | 6 | Climb | 1 |  |  | Aft | Medium | 6500 ft | Up | High | 95 | High | climb
1004 | 1004 | 6 | Glide Performance | 1 |  |  | Aft | Medium | 6500 ft | Up | Medium | 80 | Low | descent
1005 | 1005 | 15 | Engine Ground Test | 1 |  |  | Fwd | Medium | 6500 ft | Up | Medium | 80 | Medium | fly level
1006 | 1006 | 15 | Roll Control Forces | 1 |  |  | Fwd | Medium | 6500 ft | Up | Medium | 80 | Medium | fly level
1007 | 1007 | 15 | Roll Control Forces | 1 |  |  | Fwd | Medium | 6500 ft | Up | Medium | 80 | Medium | fly level
1008 | 1008 | 15 | Roll Control Forces | 1 |  |  | Fwd | Medium | 6500 ft | Up | Medium | 80 | Medium | fly level
1009 | 1009 | 2 | Short period #1 | 1 |  |  | Fwd | Medium | 6500 ft | Up | High | 95 | Medium | fly level | PUSH-PULL
1010 | 1010 | 11 | Climb | 1 |  |  | Fwd | Low | 5500 ft | UP | Medium | 80 | High | climb | -
1011 | 1011 | 11 | Climb | 1 |  |  | Fwd | Low | 5500 ft | UP | High | 95 | High | climb | -
1012 | 1012 | 11 | Climb | 1 |  |  | Fwd | Low | 5500 ft | UP | Low | 70 | High | climb | -
1013 | 1013 | 11 | Glide Performance | 1 |  |  | Fwd | Medium | 6500 ft | Up | Low | 70 | Low | descent
1014 | 1014 | 11 | Stall | 1 |  | 5 | Fwd | Medium | 6500 ft | UP | Low | 70 | Medium | fly level | - |  | Set configuration, A/C must keep attitude for 20s | Decrease power | Speed should decrease with 1kn/s | Hold altitude with elevator | Wait until attitude negative, accelerate back to initial condition | - | - | Do not exceed 111 kt | - | Wings level during whole manoeuvre
1015 | 1015 | 11 | Glide Performance | 1 |  |  | Fwd | Low | 5500 ft | Up | Low | 70 | Low | descent
Note on N31: ====== ID#AAAADLXwNOc Autor (2019-07-04 12:04:12) instead of Medium
Note on N32: ====== ID#AAAADLXwNOE Autor (2019-07-04 12:04:12) instead of Medium
Note on P104: ====== ID#AAAADLXwNOI Autor (2019-07-04 12:04:12) instead of LEFT-RIGHT
Note on P106: ====== ID#AAAADLXwNOM Autor (2019-07-04 12:04:12) instead of LEFT-RIGHT
Note on P114: ====== ID#AAAADLXwNNg Autor (2019-07-04 12:04:12) instead of LEFT-RIGHT

## ADB and Rudder Calibration
AOA |  |  |  |  | Elevator |  |  |  |  | Trim down
vane points up | -20 | 0.031 | Gain: | 668.8145 | Pitch down | 6.8 | -0.1884 | Gain: | -89.8505 |  | Elevator 6.8 | 0
| -10 | 0.045598 | Offset: | -40.2582 |  |  |  | Offset: | -10.1926 |  | Elevator -10 | 26.7
| 0 | 0.05859 |  |  |  | 0 | -0.11463
| 10 | 0.074729
vane points down | 20 | 0.09105 |  |  | Pitch up | -10 | -0.0016746 |  |  | Trim up | Elevator 6.8 | -20
[11 empty] | Elevator -10 | 12
AOS |  |  |  |  | Aileron Left
vane points right | -20 | 0.15919 | Gain: | 184.0756 | Left up | -25 | -0.35192 | Gain: | 99.7565
| -10 | 0.22005 | Offset: | -49.7401 |  | -15 | -0.28222 | Offset: | 12.0574
| 0 | 0.27016 |  |  |  | -7 | -0.20841
| 10 | 0.32218 |  |  |  | 0 | -0.12765
vane points left | 20 | 0.37949 |  |  |  | 6 | -0.045143
[5 empty] | Left down | 13
Aileron Right
[5 empty] | Right up | 25 | 0.10829
[6 empty] | 15 | 0.037771
[6 empty] | 7 | -0.040531
[6 empty] | 0 | -0.1245
[6 empty] | -6 | -0.20356
[5 empty] | Right down | -13 | -0.32684 | Gain: | 87.3306
[6 empty] | 25 | 0.10829 | Offset: | 15.5433
Rudder
[5 empty] | Rudder left | 25.5 | 0.015527
[6 empty] | 0 | -0.077481
[5 empty] | Rudder right | -30 | -0.17853 | Gain: | 286.0024
[6 empty] | 25.5 | 0.015527 | Offset: | 21.0592
[5 empty] | Power | 0 | -0.16884 | Gain: | -383.7269
[6 empty] | 25 | -0.23088 | Offset: | -61.9745
[6 empty] | 50 | -0.30236
[6 empty] | 75 | -0.38215
[6 empty] | 100 | -0.42944
[6 empty] | 0 | -0.16884